Course Name

Student Name

Tutor Name

- From the attached A3 construction program:

- List the tasks which are definitely on the critical path.

Consent issues (predicted)

Site mobilization

General building set out

Excavation

Foundations

Slab Backfill and compaction

Under floor services

Floor slab

Timber wall framing

Timber roof framing

Exterior cladding

Aluminum joinery install

Roller door installation

Service first fix

Interior linings

Finish trim

Painting

Floor covering

Defect remediation and final Clean

Client handover

- List the tasks which are definitely not on the critical path.

Exterior concrete paving

Structural steel manufacture

Structural steel erect

Roof install

Timber door install

Suspended ceiling install

Service second fix

Kitchen and bar joinery install

- Using information on the attached A3 sheet, prepare a schedule of Adjustment for Construction Instruction C.I 10 and calculate the total cost of the variation. Include a variation process fee. Present your answer in the form of a table, to industry format.

| ITEM | DESCRIPTION | UNIT | QUANTITY | RATE ($) | AMOUNT ($) |
| --- | --- | --- | --- | --- | --- |
|  | DELETE |  |  |  |  |
|  | Reception |  |  |  |  |
| A | GIB board(to concrete) | SM | 25 | 28.00 | 700.00 |
| B | Paint to GIB | SM | 25 | 23.50 | 587.50 |
| C | Timber to cornice | LM | 25 | 14.50 | 362.50 |
| D | Paint to cornice | LM | 25 | 6.00 | 150.00 |
|  | Storage |  |  |  |  |
| E | Solid plaster to concrete | SM | 15 | 59.00 | 885.00 |
| F | Paint to plaster | SM | 15 | 14.00 | 210.00 |
|  | Office |  |  |  |  |
| G | GIB board | SM | 80 | 28.00 | 2240.00 |
| H | Paint to GIB boards | SM | 80 | 12.50 | 1000.00 |
| I | Timber to cornice | LM | 36 | 14.50 | 522.00 |
|  | Paint to timber cornice | LM | 36 | 6.00 | 216.00 |
| Total added |  |  |  |  | 6873 |
|  | ADD |  |  |  |  |
|  | Reception |  |  |  |  |
| A | Grid suspended ceiling with patterned ceiling tiles | SM | 15 | 29.00 | 435.00 |
| B | Aluminum perimeter trim | LM | 25 | 21.00 | 525.00 |
|  | Storage |  |  |  |  |
| C | Painting to concrete soffit | SM | 15 | 16.00 | 240.00 |
|  | Office |  |  |  |  |
| D | Grid suspended ceiling with acoustic ceiling tiles | SM | 80 | 29.00 | 2320.00 |
| E | Aluminum perimeter trim | LM | 36 | 21.00 | 756.00 |
| Total delete |  |  |  |  | 4276 |
| Variation =6873-4276 =2597 Assume Variation processing fee of $500 2597+500 =3097 |  |  |  |  |  |

- Small House Specification in Master spec:

Prepare, using the abridge Master spec template in word, a specification for all items associated with selected sections of the CARPENTRY trade of the ‘small House’. You are to source all information necessary, including full details of workmanship and materials. Refer to additional ‘small House’ drawing at the end of this brief.

Assignment
Project Specification

SPECIFICATION of work to be done and materials to be used in carrying out the works shown on the accompanying drawings

Masterspec

CARPENTRY

1.0. GENERAL

1.1. Related Documents:

- Drawings and general provisions of the Subcontract apply to this Section.

- Review these documents for coordination with additional requirements and information that apply to work under this Section.

1.2. Quality Assurance

- Inspection:  Prior to work of this Section, carefully inspect the installed work of other trades and verify that such work is completed to the point where this installation may properly commence.

- Discrepancies:  In the event of discrepancy, immediately notify the Project Manager.  Do not proceed with installation in areas of discrepancy until such discrepancies have been fully resolved.

- Lumber may be rejected by the Project Manager, whether or not it has been installed, for excessive warp, twist, bow, crook, mildew, fungus, or mold, as well as for improper cutting and fitting.

1.3. Delivery, Storage and Handling

- Materials shall be properly packed and handled while in transit so as to arrive at the job site in undamaged condition.  Manufactured materials shall be delivered in suitable containers plainly marked with brand and manufacturer's name.

- Storage arrangements shall be subject to Project Manager's approval and shall afford every access for inspection and identification of each item.  Lumber shall be piled off the ground, on skids, in a manner which prevents twisting or warping and affords proper ventilation, drainage and protection from termites and decay, rain and excessive sun.  Plywood shall be protected from dampness.  Material shall be protected from the elements and from damage or deterioration.

- Damaged or deteriorated materials or assemblies shall not be used in the work and shall be replaced at no extra cost to University.

2.0. PRODUCTS

2.1. Materials

- General:  Material shall conform to these specifications and to the applicable current editions of the Standard Specifications

- Lumber Grade Marking: Each piece of lumber shall bear the official grade mark of the appropriate inspection

- Dimensional lumber 2 inches (50 mm) or less in thickness shall have an average moisture content of 19 percent or less but no portion of a shipment shall be over 25 percent.  Air dried lumber is desired but, if necessary, lumber may be kiln dried, however, the drying process must be slow and regulated to cause only an amount of checking comparable with air-dried stock.  Wood thicker than 2-1/2 inches (63 mm) shall be well seasoned stock, moisture content not to exceed 18 percent

- Sills and equipment curbs which rest on concrete shall be foundation grade Redwood or preservative pressure treated Douglas Fir.

- Framing, blocking, backing, etc., unless otherwise shown, shall be Douglas Fir. All interior wood and plywood used for blocking and built into roofing, or otherwise shown shall receive fire retardant pressure treatment in accordance with paragraph 2.5.B. Exterior stair framing and decking, and wood exposed to the exterior, or otherwise shown, shall receive the preservative type pressure treatment

2.2. Nails and Spikes

- Nailing of wood members shall conform to Uniform Building Code and/or as indicated.  Box nails are not permitted.

- Penetration:  half-length of nail into piece receiving point.

- To connect pieces 2 inches (25 mm) net in thickness, 16d nails may be used.

- Does not drive nail closer together than half their length, nor closer to edge of piece of lumber or timber than 1/4 their length.

- Spacing and size of nails to be such that splitting will not occur.  Pre-bore holes for nails wherever necessary to prevent splitting.                                                                                                                                                                                    For plywood nailing, barbed plywood nails, size and spacing as indicated.  Nails shall have edge distances of not less than 3/8 inch (9.5 mm).

- Use galvanized nails where exposed to weather or where members are built-in to roofing.

- Screws:  Bright steel wood screws: Screws are to be turned into place, not driven. Self-tapping where required for fastening to metal framing.

2.3. Countersink

- Screw bolt holes the same diameter and depth as shank; bore holes for threaded portion of screws with bit no larger than base of thread.

- Use galvanized or cadmium plated screws on fastenings exposed to weather or where members are built-in to roofing.

- Bolts:  Standard mild steel, square or hex head machine bolts with square nuts and malleable iron or steel plate washers, conforming to ASTM A307.

- To be installed in drilled holes the diameter of the bolt, 1/32 inch (0.8 mm) to 1/16-inch (1.6 mm) over size.

- Bolting of wood members shall conform to CBC requirements and as called for on the drawings.

- Washers:  Provide bolts bearing on wood, unless noted otherwise on the drawings, with malleable iron, or steel plate washers under heads and nuts.  Do no final bolting until structure has been properly aligned.

- Use galvanized bolts, nuts and washers where exposed to weather or where members are built-in to roofing.

- Lag Screws: Conform to "National Design Specification for Stress Graded Lumber and Its Fastenings," NFPA, latest edition.

3.0. EXECUTION

3.1. Workmanship

- General:  Rough carpentry shall produce joints true, tight, and well nailed with members assembled in accordance with the Drawings and with pertinent codes and regulations.

- Selection of lumber pieces: Carefully select members.  Select individual pieces so that knots and obvious defects will not interfere with placing bolts or proper nailing or making proper connections.

3.2. Wood Preservative

- All exterior framing and wood trims coming in contact with concrete or masonry, whether or not Redwood, and not specified or otherwise shown to be pressure treated shall be treated with ACQ Preserve®.  Preservatives shall be compatible with stain coatings when specified in Division 09 Section "Painting".

3.3. Cleanup

- At the end of each shift and upon completion of the work, remove debris, rubbish and surplus materials from the site which resulted from work under this section.  Do not leave wood, shavings, sawdust, etc. on the ground or buried in fill.  Take positive measures to ensure that saw dust and wood shavings do not enter the storm drainage system.

- Describe the formal(contractual) and procedural(managerial) relationship between:

- Main contractor and

- Domestic contractors

- The main contractor appoints the domestic subcontractor to carry out some or whole part of the project.

- The domestic subcontractor is appointed by the main contractor, (Tan, Xue and Cheung, 2017).

- The domestic subcontractor receives orders and instructions from the main contractor.

- The domestic subcontractor reports directly to the main contractor.

- The domestic subcontractor is paid by the main contractor.

- The domestic subcontractor therefore enters into an agreement with the main contractor to work on his behalves without necessarily involving the client, (Tan, Xue and Cheung, 2017)..

- Nominated subcontractor

- Nominated subcontractors are contracted in accordance with the main contract.

- The prime cost is inserted into the main contract that the nominated subcontractors will receive for the services rendered. Therefore, the main contractor is not involved in paying the nominated subcontractor. The nominated subcontractor is paid directly by the client.

- The appointment of the nominated subcontractor is done by the client or his appointee and therefore the main contractor has no legal obligation to appoint the nominated subcontractor.

- The nominated subcontractor has no contractual agreement with the main contractor and therefore need not to report him on the progress of the work

- Main contractor and client

The main contractor and the client enter into an agreement in which the client provides adequate resources such as land, money and any other resources for the contractor to execute his responsibilities.

The client has the responsibility of paying the contractor on time to allow normal progress of work

The contractor reports to the client the progress of the work in regular basis according to the contractual agreement.

The client is the boss and he gives all instructions regarding the project in consultation with his consultancy team.

- Main contractor and Architect(lead consultant)

- The Architect (lead consultant) should inspect work done by the contractor to ensure that they conform to the specifications and the drawings. If he is not satisfied with the work, he should give instruction to the contractor.

- The contractor should adhere and comply with all instructions issued by the Architect (lead consultant)

- The contractor should report to the Architect (lead consultant) on regular basis on the progress of work.

- In case of variation, the Architect (lead consultant) has a responsibility of providing relevant documents to the contractor within reasonable time.

- Main contractor QS and client QS

- The Main contractor QS and client QS are responsible in ensuring that construction cost is reasonable making it possible for the project to run smoothly, (Mbachu, 2015)

- They work together in case of variation to come up with the sum to be paid to the contractor

- The client QS ensure that the amount paid to the contractor is equivalent to the job done.

- The client and the contractors QS work together to control cost of the project.

- The client and contractor QS manages money paid to the nominated subcontractor,

- The client QS is consulted early in the project to do a project visibility test and ensure that the project is worth doing.

- Referring to NZIQS code of conduct(July 2017),

- List out the six scopes covered

The scopes covered in the NZIQS are: Introduction, Definitions, Application of The Code, Professional Conduct, Competence and Client Care and Confidential Information, (NZIQS Code of Conduct, 2017).

- Explain what constitute conflict of interest and give at least 3 circumstances

Circumstances that constitute conflict of interest include:

a) Acting, for remuneration or other reward, for more than one party in respect of any particular work;

b) Acting in conﬂicting positions on the same work;

c) Pricing for another party any part of a Schedule of Quantities prepared in the member’s office or place of employment or by the member’s firm except on behalf of the client commissioning the original work;

d) Undertaking the pricing of any Schedule of Quantities prepared by another firm for the same works, for more than one client;

e) Having any financial interest in any organization with which they may have occasion to deal on behalf of their client, (NZIQS Code of Conduct, 2017).

.

- If conflict of interest is identified, explain how to handle it as a professional

Where a conﬂict of interest arises or a member identifies circumstances that could be construed as a conﬂict of interest, the member must:

a) Inform the client, and any other interested party, of the actual or potential conﬂict of interest;

b) Encourage the client to obtain independent professional advice; and

c) Not act or continue to act for the client unless the client provides written instructions and consent that acknowledges the actual or potential conﬂict, (NZIQS Code of Conduct, 2017).

References

Camén, C., Gottfridsson, P., & Rundh, B. (2011). To trust or not to trust? Formal contracts and the building of long-term relationships. Management Decision, 49(3), 365-383.

Halpin, D. W. (2010). Construction management. John Wiley & Sons.

Lahdenperä, P. (2012). Making sense of the multi-party contractual arrangements of project partnering, project alliancing and integrated project delivery. Construction Management and Economics, 30(1), 57-79.

Mbachu, J. (2015). Quantity Surveyors‟ Role in the Delivery of Construction Projects: A Review. Quantity Surveyors (NZIQS), 25.

Nielsen, B. B. (2010). Strategic fit, contractual, and procedural governance in alliances. Journal of Business Research, 63(7), 682-689.

NZIQS Code of Conduct. (2017). Retrieved from https://www.nziqs.co.nz/About-Us/Code-of-Conduct

Schepker, D. J., Oh, W. Y., Martynov, A., & Poppo, L. (2014). The many futures of contracts: Moving beyond structure and safeguarding to coordination and adaptation. Journal of Management, 40(1), 193-225.

Tan, Y., Xue, B., & Cheung, Y. T. (2017). Relationships between main contractors and subcontractors and their impacts on main contractor competitiveness: an empirical study in Hong Kong. Journal of Construction Engineering and Management, 143(7), 05017007.