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Non-profit Mission Statement
Housing Homeless Veterans in Kentucky is driven by the desire to provide housing, healthcare and sustainable solutions to all the homeless veterans with in the State of Kentucky.
Executive Summary
	Following the rising number of homeless veterans in Kentucky, the Kentucky Housing Corporation in conjunction with other nonprofit organizations and government agency developed this program to address this issue. The program will involve the resettlement of all the homeless veterans into new houses with different communities; providing healthcare services and training them for sustainable livelihood.
Program Title/Review
Housing Homeless Veterans in Kentucky
Staffing
	Title
	Budgeted
	Actual
	Difference
	Comments

	Executive project manager
	1
	1
	0
	Job ad posted

	Project Management staff
	4
	3
	1
	Job ad posted

	Field officer, veterans' affairs
	8
	9
	-1
	Assessment of applicants in progress

	Community Social workers 
	10
	12
	-2
	Assessment of applicants in progress

	Mental Health Social worker
	4
	4
	0
	Assessment of applicants in progress

	Sheltered Workshop Supervisor Trainers
	5
	5
	0
	Assessment of applicants in progress



Budget
	Item
	Budgeted
	Actual
	Difference
	Comments

	Personnel (Staff or Contractors)
	$ 555,500
	$ 600,000
	-$45,000
	Still advertising for jobs

	Duplication and Printing
	$ 85,000
	$ 70,000
	$ 1,500
	All the materials for printing and duplicating have been procured.

	Rental
	$ 2,000
	$ 3,000
	$ -1,000
	The computers necessary for this program have been procured

	Advertising
	$ 850
	$ 2000
	$ 1,150
	The first campaign in the community program was conducted and received eighty percent approval from the communities.

	Utilities, Telecommunications
	$ 80,000
	$ 80,000
	$ 80,000
	This Materials have not yet been procured

	Supplies
	$ 210,000
	$ 180,000
	$ 30,000
	So far the projects has received and electricity supply and medical supply.



Additional Item
Resettlement program
	[bookmark: _GoBack]Program
	Clients Settled
	Target Number
	Clients Remaining
	Comments

	Phase 1
	25
	50
	25
	The first phase of the resettlement program has kicked off successfully. Have all the targeted number for the first quarter of the year have been resettled.

	Phase 2
	0
	70
	85
	This program is yet to commence

	Phase 3
	0
	60
	70
	This program is yet to commence
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