Housing Homeless Veterans in Kentucky Quarterly Report Card

Non-profit Mission Statement

Housing Homeless Veterans in Kentucky is driven by the desire to provide housing, healthcare and sustainable solutions to all the homeless veterans with in the State of Kentucky.

Executive Summary

Following the rising number of homeless veterans in Kentucky, the Kentucky Housing Corporation in conjunction with other nonprofit organizations and government agency developed this program to address this issue. The program will involve the resettlement of all the homeless veterans into new houses with different communities; providing healthcare services and training them for sustainable livelihood.

Program Title/Review

Housing Homeless Veterans in Kentucky

Staffing

| Title | Budgeted | Actual | Difference | Comments |
| --- | --- | --- | --- | --- |
| Executive project manager | 1 | 1 | 0 | Job ad posted |
| Project Management staff | 4 | 3 | 1 | Job ad posted |
| Field officer, veterans' affairs | 8 | 9 | -1 | Assessment of applicants in progress |
| Community Social workers | 10 | 12 | -2 | Assessment of applicants in progress |
| Mental Health Social worker | 4 | 4 | 0 | Assessment of applicants in progress |
| Sheltered Workshop Supervisor Trainers | 5 | 5 | 0 | Assessment of applicants in progress |

Budget

| Item | Budgeted | Actual | Difference | Comments |
| --- | --- | --- | --- | --- |
| Personnel (Staff or Contractors) | $ 555,500 | $ 600,000 | -$45,000 | Still advertising for jobs |
| Duplication and Printing | $ 85,000 | $ 70,000 | $ 1,500 | All the materials for printing and duplicating have been procured. |
| Rental | $ 2,000 | $ 3,000 | $ -1,000 | The computers necessary for this program have been procured |
| Advertising | $ 850 | $ 2000 | $ 1,150 | The first campaign in the community program was conducted and received eighty percent approval from the communities. |
| Utilities, Telecommunications | $ 80,000 | $ 80,000 | $ 80,000 | This Materials have not yet been procured |
| Supplies | $ 210,000 | $ 180,000 | $ 30,000 | So far the projects has received and electricity supply and medical supply. |

Additional Item

Resettlement program

| Program | Clients Settled | Target Number | Clients Remaining | Comments |
| --- | --- | --- | --- | --- |
| Phase 1 | 25 | 50 | 25 | The first phase of the resettlement program has kicked off successfully. Have all the targeted number for the first quarter of the year have been resettled. |
| Phase 2 | 0 | 70 | 85 | This program is yet to commence |
| Phase 3 | 0 | 60 | 70 | This program is yet to commence |