## Sheet1
RISK REGISTER TEMPLATE
REF ID | RISK | RISK OWNER | WBS ID | Item at Risk | RISK CATEGORY | PROBABILITY 1 – 3 | IMPACT 1 – 3 | PI SCORE Prob x Impact | Mitigation Action | POSITIVE RISK RESPONSE | NEGATIVE RISK RESPONSE | RESPONSE OWNER | RESPONSE DESCRIPTION | EXPECTED RESPONSE IMPACT
R/MNG/1 | Poor definition of project purpose and need | Project manager | WB 1.1 | Project Initiation Phase | managerial risk | 1 | 3 | 3 | conduct initial meetings with the stakeholders to go through all aspects of the project | ENHANCE | AVOID | project Manager | communicate with the sponsor and the stakeholders to seek clarification before initiating the implementation phase | will make the stakeholders offer clear definitions, hence avoiding ambiguity in the consecutive phases of the project
R/MNG/2 | identification of inappropriate team members | Project manager | WB 1.1.1 | Project Team | managerial risk | 2 | 3 | 6 | run background checks for qualifications of the team members | ENHANCE | AVOID | project manager | abandon the team members and recruit new ones | provide qualified team which will help in minimizing the risks and providing quality work
R/MNG/3 | incomplete project design and deliverables definition | Project Manager/ Sponsor | WB 1.2 | Project Management Phase | managerial risk | 2 | 3 | 6 | constant communication with the project sponsor to ensure that all deliverables are adequately defined | ENHANCE | MITIGATE | project manager | meet with the stakeholders (client) to obtain comprehensive project design and deliverables | wil lead to the delivery of the client's intended deliverables, hence promoting clarity and satisfaction of the client with the project
R/EXT/1 | scope creep | Sponsor | WB 1.21 | Project Scope | external risk | 2 | 3 | 6 | Ensure that the scope is clear to every stakeholder of the project | EXPLOIT | MITIGATE | project manager/ sponsor | meet with the stakeholder and the project team to explain to them the details of the project scope in details. In this case, clarify what is and what is not in the scope | will ensure that each stakeholder has clarity of the scope, thereby avoiding several cases of project crep
R/EXT/2 | pressure to arbitrarily reduce task duration and or run tasks in parallel which would increase risk of errors | Sponsor | WB 1.2.1.4 | Review Finalized Project Scope with Project Sponsor | external risk | 2 | 3 | 6 | use time management tools such as WBS to ensure all tasks are allocated enough time | ACCEPT | TRANSFER | project manager | engage the client and the involved stakeholders, explaining to them the adverse effects of the pressure. Also ask for additional support resource if the tasks are to be run parallel | will ensure that there is enough resources needed for the running of parallel tasks, hence reducing the risks of errors
R/Q/1 | poor identification of project requirements | Project manager | WB 1.3 | Project Requirements Phase | quality risk | 1 | 3 | 3 | allocate sufficient time to go through all the deliverables and consult professionals as well as the team-members on the project requirements | ENHANCE | AVOID | project manager | consult the project team members (both technical and managerial) to help in identifying all the requirements. Utilize tools such as the WBS and task lists to ensure that all requirements are identified and planned for | wil; ensure that all the requirements are captured, hence rteducing the cases of the project becoming ineffective due to lack of identification of all requirements
R/0RG/1 | conflict in the system requirements between the project team and the organization's IT department | Project members | WB 1.3.2.2.2 | Review and Finalize Clover POS Requirements | organization risk | 2 | 3 | 6 | engage the IT department in the planning phase to ensure that they are on board with the system requirements | EXPLOIT | TRANSFER | project manager and the organization | organize a meeting between the project team and the IT department, in the presence of a mediator to explain to the IT on the requirements of the proposed project, and the need for the two teams to work together in collaboration for the project to be successful | will help in speedy conflict resolution, which will give the project team sufficient time to proceed with the remaining phases of the project
R/EXT/3 | Delays of design and permits | Developers | WB 1.4.2 | Development Iteration 2 | external risk | 2 | 2 | 4 | allocate sufficent time in the initial planning phase for obtaining the required permit | ACCEPT | MITIGATE | developers | make appropriate follow ups to the authorities in charge of permits, at the same time encouraging the team members (dfevelopers) to speed up their design | will help in speeding up the proces of obtaining the permit to enable other phases of the project to continue
R/TCH/2 | incompatibility with the current system | Developers | WB 1.5.1.1 | Installation | technical risk | 1 | 3 | 3 | run background check of the current system to determine the design and the properties and identify the likelihood of the incompatibility | ENHANCE | AVOID | developers | reevaluate the current and the new software systems requirements to identify areas of incompatibility and take the apprpriate corrective measures to ensure that the systems are compatible. | will help in ensuring that the installed system are compatible with the current systems, hence leading to the project being valuable to the organization
R/ORG/2 | unwilling participation in training by employees | Project Manager/ Organization | WB 1.5.4.4 | Training | organization risk | 2 | 3 | 6 | inform the management to make early communoication about the intention of adopting the two software systems, clarifying to them that they will be trained as a result of the change process | EXPLOIT | TRANSFER | project manager and organization | consult the organization, and encourgae the management to follow the change process, whoch will help in convincing the employees of the importance of adopting the new systems, hence the need for training. | will ensure that employees willingly and actively participate in the training sessions
R/EXT/4 | delays in the delivery of the Syspro ERP | Suppliers | WB 1.3.2.1 | SysPro ERP | external risk | 2 | 3 | 6 | make sufficient allocation of time for obtaining the system and look for providers that make the earliest and most favorable delivery | ACCEPT | ACCEPT | project manager | contact the suppliers of the software, informing them of the inconveniences they are causing, giving them the deadline, which woul lead to cancellation of the order if they fail to deliver by then | will speed up the process of delivering the software, hence enabling the project to continue as per the WBS plan
R/PRJ/1 | Misunderstandings about what a normal project entails | Organization | WB 1.4.3.2 | Develop, Test and Debug Work Package 3 | project risk | 3 | 2 | 6 | make it known to all the stakeholders that bugs (issues) are part of the project, hence the need to have the initial tests | EXPLOIT | ACCEPT | project manager | conduct a meeting with the organization stakeholders to explain to them that the bugs are a normal part of a project, hence the need of conducting tests to heelp in identifying the bugs and fixing them before the final projec tdelivbery | will help in ensuring that the stakehollders have comprehensice knowledge pf the project, enabling the project team to have sufficient time for identification and correction of the problems
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0