## Instructions
Risk Register Workbook Instructions
This template is to be used for identifying risks and creating plans for how to avoid them (negative risks) or how to make them happen (positive risks) and what to do if they happen (contingency plans) and managing them throughout the project.
The first sheet, titled Risk Register, shows a number of fields to use for gathering the following information about risks.
Risk ID is some unique value that identifies the risk.
Risk Name is a short description of the risk.
Risk Description "If this risk occurs, then what impact will it have on the project?" It should be written as an "If, then" statement.
Impact as rated on a very low, low, medium, high, and very high scale.
Probability as rated on a very low, low, medium, high, and very high scale.
Risk Ranking: Using the risk matrix found on the right on the Risk Register sheet, detemine the color code (risk ranking) for each risk.
Positive/Negative: Is this risk a positive risk (an opportunity) or a negative risk?
Proactive Response Plan is a detailed plan of what changes will be made to the project, project scope, and/or WBS proactively to try to make the risk happen (positive risk) or stop it if it is a negative risk.
Trigger Event is a description of how you will know if the risk has occurred or is about to occur.
Reactive Contingency Plan is the description of what you plan to do if the risk happens. How will you react to the risk once it occurred?

## Risk Register
Risk Register
ID | Risk Name | Risk Description | Impact | Probability | Risk Ranking | Positive/Negative | Proactive Response Plan | Trigger Event | Reactive Contingency Plan
|  |  | VH,H,M,L,VL | VH,H,M,L,VL | What is the risk color code ? | Is this a positive or negative risk from the risk matrix? | What proactively can be attempted to make the risk happen or prevent it? | What do you think will trigger the event? | What are your backup plans if the risk should occur?
1 | More than optimistic employee workload | When employees are given a wide workload within a short time. The possibility is a low outcome | H | H | Red | Negative | Taking advantage of the digitalized globe to seek for capacity building training by taking care of all risks | High demand | By counting overtime pay
2 | Inadequate development skills | when workers are exposed to new working environment they tend to have less skills needed. Thus inadequecy in skills. | H | H | Red | Positive | training of the employees by worksops, involving SMEs | Exposure to new environment | Engaging experts for apprecetiship
3 | Schedule overrun | this is mostly influenced when demand of products in very high. | M | VL | Green | Positive | Increasing the employees by sourcing from other centers of the same company. | This happens due to high expectation and high demands of services and products. | Adding the overtime incentive
4 | Lower anticipated financial payback | when the feasibility study is not adequetly done it results to less than expectd outcome. | H | M | Yellow | Negative | Training the project manager on Agile feature to increase payback cash. | Applying phased out features in digitalised projects. | accounting for contigencies at time of the initial plan. |  | Very high
5 | Site not on google market search | This is because the products are not provided for by SEO and google mapping. | H | M | Yellow | Negative | Advertise on real time digital marketing platforms like facebook, twitter and SEO | Less IT experts on site | Use available platforms to enhance accessiblity and visibility |  | High
6 | Design conflict among team members | Inadequate flow of communication between the leadership of the company. | H | M | Yellow | Positive | Providing training of the same nature to orient the minds of the team members | Involving different experts to work on the ssame project. This is because they don't have the same skills and competencies. | The design leader provide for expert judgement on the conflicting issue by inviting expert to the site. |  | Medium
7 | Incorrect customer information | This influence the customers from making correct market decision | H | H | Red | Negatiive | Contacting the customer care service desk | Information handed over with some errors which costs more to rectify. | Asking customers to obtain the correct information from the relations personnel or the customer care desk. | Impact | Low
8 | Lack of staff adequate knowledge on products | This is brought by employees experiencing less orientation to work place. | M | L | Green | Positive | Intensive orientation to work place activities, products, services, routines and rule that govern the daily operations. | High demand to manpower due to increased demnd in products and services. | Providing a more knowledgable worker to facilitate the urgent tasks |  | Very low
9 | Acceptance of unrealistic contract deadlines | This is due to high competition with other bidders and experienced workers. | H | VH | Red | Positive | Seeking the right contractual information from the faculty provisions. | Provision of less or false cotractual information. | Employing other workers. |  |  | Very low | Low | Medium | High | Very high
10 | Underestimated budgets | This is caused by inadequate information on prices of commodities | H | VH | Red | Negatiive | Taking into account of every minute aspect of the proposal including contigencies. | This is due to limiting the capacity or scope of the proposed definitions. | Hire experts for design and valuations.
Probability
Risk Matrix
Note on C2: If the risk occurs, what will happen to the project?
Note on F2: What is the risk's color code from the risk matrix on the right?
Note on G2: Is this positive risk or a negative risk?
Note on H2: What will you do proactively to address the risk?
Note on I2: How do we know when the risk event has happened? What indications can we look for?
Note on J2: If the event occurs, what can we do to address the effects of the risk?