## Instructions
Risk Register Workbook Instructions
This template is to be used for identifying risks and creating plans for how to avoid them (negative risks) or how to make them happen (positive risks) and what to do if they happen (contingency plans) and managing them throughout the project.
The first sheet, titled Risk Register, shows a number of fields to use for gathering the following information about risks.
Risk ID is some unique value that identifies the risk.
Risk Name is a short description of the risk.
Risk Description "If this risk occurs, then what impact will it have on the project?" It should be written as an "If, then" statement.
Impact as rated on a very low, low, medium, high, and very high scale.
Probability as rated on a very low, low, medium, high, and very high scale.
Risk Ranking: Using the risk matrix found on the right on the Risk Register sheet, detemine the color code (risk ranking) for each risk.
Positive/Negative: Is this risk a positive risk (an opportunity) or a negative risk?
Proactive Response Plan is a detailed plan of what changes will be made to the project, project scope, and/or WBS proactively to try to make the risk happen (positive risk) or stop it if it is a negative risk.
Trigger Event is a description of how you will know if the risk has occurred or is about to occur.
Reactive Contingency Plan is the description of what you plan to do if the risk happens. How will you react to the risk once it occurred?

## Risk Register
Risk Register
ID | Risk Name | Risk Description | Impact | Probability | Risk Ranking | Positive/Negative | Proactive Response Plan | Trigger Event | Reactive Contingency Plan
|  |  | VH,H,M,L,VL | VH,H,M,L,VL | What is the risk color code ? | Is this a positive or negative risk from the risk matrix? | What proactively can be attempted to make the risk happen or prevent it? | What do you think will trigger the event? | What are your backup plans if the risk should occur?
1 | Example: please remove before completing document. Critical equipment does not arrive on time. | If critical pieces of equipment do not arrive on time, the project will fall behind schedule. | H | H | Red | Negative | 1. Add activities to the WBS to ensure with the manufacturer that the equipment is being built or shipped as required. 2. Have a member of project team go to the manufacturing plant to ensure equipment parts are in progress and on schedule. 3. Add steps to the WBS to ensure the manufacturer ships on time. 4. Add steps to WBS to track the shipment as needed. | Parts do not ship on assigned date. | If possible, have a backup supplier identified and standing by.
2
3
4 | [10 empty] | Very high
High
Medium
[10 empty] | Impact | Low
Very low
[12 empty] | Very low | Low | Medium | High | Very high
Probability
Risk Matrix
Note on C2: If the risk occurs, what will happen to the project?
Note on F2: What is the risk's color code from the risk matrix on the right?
Note on G2: Is this positive risk or a negative risk?
Note on H2: What will you do proactively to address the risk?
Note on I2: How do we know when the risk event has happened? What indications can we look for?
Note on J2: If the event occurs, what can we do to address the effects of the risk?