Starting a Business / ASP 5861

Starting and Managing a Business (Competency 7)	946-563

Worksheet 3 – Synthesis Phase Due Date: _____________________

Candidate’s Name: Centre: Permanent Code:

| ACTION PLAN FOR STARTING A BUSINESS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL #1: Create a budget plan |  |  |  |  |  |  |  |  |
| Action: | Responsible | Timeframe/Deadline Start/End |  | Priority Low/Medium/High | Resources (staff, tech) | Budget/Cost | Status Not Started/In Progress Incomplete/Complete | Notes |
| Steps |  |  |  |  |  |  |  |  |
| - Identifying revenue sources | Business owner | January | January | High | Sponsors | $2,000 | Complete | Aimed at determining where to source the capital |
| - Research on products and services to be offered | Marketing manager | January | January | High | Research and development staff | $10,000 | Complete | Helped to decide on the right products and services to invest funds |
| - Determine price tag of the products | Marketing manaager | January | January | High | Marketing department | $0 |  | Price setting is essential because it helps the firm set reasonable prices |
| GOAL #2: Recruitment of working team |  |  |  |  |  |  |  |  |
| Action: | Responsible | Timeframe/Deadline Start/End |  | Priority Low/Medium/High | Resources | Budget/Cost | Status Not Started/In Progress Incomplete/Complete | Notes |
| Steps |  |  |  |  |  |  |  |  |
| - Determining the number of employees needed | Human resource manager | January | January | High | Human resource manager |  | Complete | Helped to determine the correct number of vacancies available |
| - Advertising job vacancies | IT manager | January | January | Medium | IT department | $1,500 | Complete | To make qualified people aware of the recruitment |
| - Section of the team | Human resource manager | February | February | High | Human resource manager | $1,000 | Complete | Essential in selecting the most qualified candidates |

| ACTION PLAN FOR STARTING A BUSINESS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL #3: Customer relation |  |  |  |  |  |  |  |  |
| Action: | Responsible | Timeframe/Deadline Start/End |  | Priority Low/Medium/High | Resources (staff, tech) | Budget/Cost | Status Not Started/In Progress Incomplete/Complete | Notes |
| Steps |  |  |  |  |  |  |  |  |
| - Identifying customers | Marketing manager | February | December | High | Marketing staff | $1,000 | In progress | Helps determine the potential customers |
| - Close interaction | Marketing staff | February | December | High | Marketing staff |  | In progress | Helps identify customer needs |
| - Providing feedback | Marketing staff | February | December | High | Marketing staff | $500 | In progress | Promotes customer satisfaction |
| GOAL #4: Production of quality products |  |  |  |  |  |  |  |  |
| Action: | Responsible | Timeframe/Deadline Start/End |  | Priority Low/Medium/High | Resources | Budget/Cost | Status Not Started/In Progress Incomplete/Complete | Notes |
| Steps |  |  |  |  |  |  |  |  |
| - Acquiring better equipment | Procurement manager | February | February | High | Procurement staff | $150,000 | Complete | Helps produce better and quality products |
| - Training employees on the equipment use | Human resource manager | February | March | High | Production specialist | $20,000 | Complete | Helps equip employees with necessary skills |
| - Actual production | Production manager | February | December | High | Production staff | $200,000 | In progress | Involves producing quality products that satisfy customers |

| ACTION PLAN FOR STARTING A BUSINESS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL #5: Audit reviews |  |  |  |  |  |  |  |  |  |
| Action: | Responsible | Timeframe/Deadline Start/End |  | Priority Low/Medium/High | Resources (staff, tech) | Budget/Cost |  | Status Not Started/In Progress Incomplete/Complete | Notes |
| Steps |  |  |  |  |  |  |  |  |  |
| - Selection of the audit team | Board members | Feb | May | High | Board members | $800 |  | In progress | Helps select the most qualified auditing team |
| - Conducting company audit | Audit manager | June | June | High | Audit team | $1,000 |  | Not started | Essential in accounting the company funds |
| - Taking the necessary actions | Accounting manager | June | December | High | Accounting department | $500 |  | Not started | Helps departments be accountable of all finances. |
| GOAL #6: Business Promotion |  |  |  |  |  |  |  |  |  |
| Action: | Responsible | Timeframe/Deadline Start/End |  | Priority Low/Medium/High | Resources (staff, tech) | Budget/Cost | Status Not Started/In Progress Incomplete/Complete |  | Notes |
| Steps |  |  |  |  |  |  |  |  |  |
| - Advertising the business through media means | Marketing manager | January | June | High | Marketing manager | $30,000 | In progress |  | Advertising will create awareness of the business and the products and services offered to many people. |
| - Sales promotion of the products | Marketing manager | January | March | High | Marketing department | $40,000 | In progress |  | Sales promotion will be aiming to create new prospects and boost company sales. |
| - Public relation in the market | Managing manager | January | December | Low | Marketing department | $25,000 |  |  | Public relation aims at creating awareness and reminding people about the company. |

Requirement: Sufficient and pertinent information.	Yes  No

(3.1)

Note to the Examiner: Transfer the result to the candidate’s Evaluation Form.