EXAMPLE FORMAT AND ONE COMMENT RE: OWNER’S EDITS TO A102

FINAL EXAM TAKE HOME CONTRACT REVIEW

AIA A102

- § 2.2.2 the Owner added a new provision which reads as follows:

§ 2.2.2 The Contractor shall perform all construction necessary to result in a completed and functioning Project including, without limitation, fully operational and functional components, notwithstanding, among other things, errors, omissions, inconsistencies, or lack of coordination in the Drawings and Specifications that an experienced contractor that has constructed many similar projects could reasonably have recognized during bidding and negotiation of the Guaranteed Maximum Price (together, “Discoverable Errors”). Therefore, the Contractor represents that if it encounters any Discoverable Errors, the Contractor shall promptly report them to the Owner, however, the cost to perform any additional Work necessary to complete the Project, or any increase in the cost of Work resulting from any impact on other Work or any additional Work necessary to complete the Project shall not constitute a Cost of the Work and shall not form the basis for an increase in the Guaranteed Maximum Price or Contract Time.

I would recommend deleting this added provision in its entirety, or at a minimum, significantly editing it due to the following:

- It attempts to shift design responsibility onto the contractor by stating that “Contractor shall perform all construction necessary to result in a completed and functioning Project”.  As the Contractor, I should be able to rely upon the adequacy of the design so that if I build per the design, the project will function as intended.  This language seems to say the opposite – that as the contractor I am responsible for all construction necessary to result in a functioning project.  What if I build per the design and a design error results in the project NOT functioning? This language seems to say I still have to fix it.  This basically negates the Spearin Warranty.

- It also attempts to say that as the GC, I don’t even get paid to correct design errors, but instead, I have a duty to fix “Discoverable Errors”, to include errors in the plans/design.

- The term “could reasonably have recognized” is a big problem.  This will lead to the Owner claiming that I, as the GC, should have discovered some design issue.  The only design issues/errors I should be on the hook for are those that I ACTUALLY discover – that is what the form AIA language provides and we need to go back to it.