| ID |  | Task Mode | Task Name |  | Duration | Start | Finish | Predecessors Jan 24, | Resource Names '21 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0 |  |  | Project Management for |  | 58 days | Mon 2/15/21 | Wed 5/5/21 |  |  |  |  |  |
| 1 |  |  | Initiating |  | 3 days | Mon 2/15/21 | Wed 2/17/21 |  |  |  |  |  |
| 2 |  |  | Identify Key Stakeholders |  | 1 day | Mon 2/15/21 | Mon 2/15/21 |  |  |  |  |  |
| 3 |  |  | Charter |  | 2 days | Mon 2/15/21 | Tue 2/16/21 |  |  |  |  |  |
| 4 |  |  | Planning |  | 5 days | Wed 2/17/21 | Tue 2/23/21 | 2 |  |  |  |  |
| 5 |  |  | Team Planning Meeting |  | 1 day | Wed 2/17/21 | Wed 2/17/21 |  |  |  |  |  |
| 6 |  |  | Prepare team contract |  | 2 days | Thu 2/18/21 | Fri 2/19/21 | 5 |  |  |  |  |
| 7 |  |  | Scope statement |  | 1 day | Mon 2/22/21 | Mon 2/22/21 | 6 |  |  |  |  |
| 8 |  |  | WBS |  | 1 day | Wed 2/17/21 | Wed 2/17/21 |  |  |  |  |  |
| 9 |  |  | Schedule and cost baseline |  | 13 days | Tue 2/16/21 | Thu 3/4/21 |  |  |  |  |  |
| 10 |  |  | Task Resource |  | 3 days | Tue 2/16/21 | Thu 2/18/21 |  |  |  |  |  |
| 11 |  |  | Task Durations |  | 6 days | Thu 2/18/21 | Thu 2/25/21 |  |  |  |  |  |
| 12 |  |  | Task dependecies |  | 1 day | Fri 2/26/21 | Fri 2/26/21 |  |  |  |  |  |
| 13 |  |  | Draft Gantt Chart |  | 2 days | Fri 2/26/21 | Mon 3/1/21 |  |  |  |  |  |
| 14 |  |  | Final Gantt chart |  | 1 day | Wed 3/3/21 | Wed 3/3/21 |  |  |  |  |  |
| 15 |  |  | Executing |  | 12 days | Fri 3/5/21 | Mon 3/22/21 | 4 |  |  |  |  |
| Project: Project Management fo Date: Sun 3/20/21 |  |  |  | Task Inactive Summary Split Manual Task Milestone Duration-only Summary Manual Summary Rollup Project Summary Manual Summary Inactive Task Start-only Inactive Milestone Finish-only External Tasks External Milestone Deadline Progress Manual Progress |  |  |  |  |  |  |  |  |

| ID |  | Task Mode | Task Name |  | Duration | Start | Finish | Predecessors Jan 24, | Resource Names '21 | Feb 7, '21 Feb 21, ' FWMS |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 16 |  |  | Survey |  | 1 day | Fri 3/5/21 | Fri 3/5/21 |  |  |  |  |  |
| 17 |  |  | User inputs |  | 1 day | Mon 3/8/21 | Mon 3/8/21 |  |  |  |  |  |
| 18 |  |  | Intranet site contnent |  | 32 days | Fri 3/5/21 | Mon 4/19/21 |  |  |  |  |  |
| 19 |  |  | Templates and Tools |  | 5 days | Fri 3/5/21 | Thu 3/11/21 |  |  |  |  |  |
| 20 |  |  | Articles |  | 3 days | Fri 3/5/21 | Tue 3/9/21 |  |  |  |  |  |
| 21 |  |  | Links |  | 2 days | Fri 3/5/21 | Mon 3/8/21 |  |  |  |  |  |
| 22 |  |  | Ask the Expert |  | 1 day | Fri 3/5/21 | Fri 3/5/21 |  |  |  |  |  |
| 23 |  |  | User request feature |  | 1 day | Fri 3/5/21 | Fri 3/5/21 |  |  |  |  |  |
| 24 |  |  | Intranet site design |  | 5 days | Fri 3/5/21 | Thu 3/11/21 |  |  |  |  |  |
| 25 |  |  | Intranet site construction |  | 6 days | Fri 3/5/21 | Fri 3/12/21 |  |  |  |  |  |
| 26 |  |  | Intranet site testing |  | 3 days | Fri 3/5/21 | Tue 3/9/21 |  |  |  |  |  |
| 27 |  |  | Intranet site testing |  | 3 days | Mon 3/8/21 | Wed 3/10/21 |  |  |  |  |  |
| 28 |  |  | Intranet site roll-out |  | 2 days | Wed 3/17/21 | Thu 3/18/21 |  |  |  |  |  |
| 29 |  |  | Project benefits measurement |  | 1 day | Mon 4/19/21 | Mon 4/19/21 |  |  |  |  |  |
| 30 |  |  | Monitoring and Controlling |  | 2 days | Tue 4/20/21 | Wed 4/21/21 |  |  |  |  |  |

| 31 |  |  | Progress Reports |  | 1 day | Tue 4/20/21 | Tue 4/20/21 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 32 |  |  | Change request |  | 1 day | Wed 4/21/21 | Wed 4/21/21 | 31 |  |  |  |  |
| 33 |  |  | Closing |  | 3 days | Thu 4/22/21 | Mon 4/26/21 | 32 |  |  |  |  |
| 34 |  |  | Prepare final project report |  | 1 day | Tue 4/27/21 | Tue 4/27/21 |  |  |  |  |  |
| 35 |  |  | Prepare final project |  | 1 day | Wed 4/28/21 | Wed 4/28/21 | 34 |  |  |  |  |
| 36 |  |  | Lessons learned |  | 1 day | Wed 5/5/21 | Wed 5/5/21 |  |  |  |  |  |