## Sheet1
Quarter | Q2-2014 | Q3-2014 | Q4-2014 | Q1-2015 | Q2-2015 | Q3-2015 | Q4-2015 | Q1-2016 | Q2-2016 | Q3-2016 | Q4-2016 | Q1-2017 | Q2-2017 | Q3-2017 | Q4-2017 | Q1-2018 | Q2-2018 | Q3-2018 | Q4-2018 | Q1-2019 | Q2-2019 | Q3-2019 | Q4-2019 | Q1-2020 | Q2-2020 | Q3-2020 | Q4-2020 | Q1-2021 | Tot Est Cost | Actual Cost | Variance
Initialize Project | 11744.4 | [27 empty] | 11744.4
Project Planning | 15510.22 | 10443.9 | [26 empty] | 25954.12
Execute & Control Project
Phase 1 - System Architecture |  | 130523.28 | 56260 | [25 empty] | 186783.28
Phase 2 - Procure Hardware & Software Resources |  |  | 7762.08 | [25 empty] | 7762.08
Resources for DEV Hardware & Software |  |  | 72400 | [25 empty] | 72400
Resources for PRD Hardware & Software |  |  | 42350 | [25 empty] | 42350
Phase 3 - Database Development |  |  | 36524.8 | 3652.48 | [24 empty] | 40177.28
Phase 4 - Develop Modules - Super Bill
Develop Patient Registration Module |  |  |  | 59849.3 | [24 empty] | 59849.3
Develop Patient Processing Module |  |  |  | 63400.24 | [24 empty] | 63400.24
Phase 5 - Super Bills-Billing Module & Insurance Claim Module
Develop Billing Module |  |  |  | 19481.28 | 126177.36 | [23 empty] | 145658.64
Develop Insurance Claim Module |  |  |  |  | 32468.8 | [23 empty] | 32468.8
Establish Maintenance Operations | [5 empty] | 96920.24 | [22 empty] | 96920.24
Phase 6 - Build Financial Module & Clinical Records Module
Develop Financials Modules | [5 empty] | 36689.6 | 31977.6 | 1268.4 | [20 empty] | 69935.6
Develop Clinical Records Module | [6 empty] | 75084.16 | [21 empty] | 75084.16
Phase 7 - Build Reporting Module | [6 empty] | 62943.44 | 37979.52 | [20 empty] | 100922.96
Phase 8 - Maintnance, Support & Training
Establish Help Desk Operation |  |  |  |  | 6951.6 | 14701.23 | 19982.08 | 21108.24 | [20 empty] | 62743.15
Establish Training Operations | [5 empty] | 13678.32 | 28778.64 | 21108.24 | [20 empty] | 63565.2
Establish Maintenance Operations | [5 empty] | 5097.84 | 7045.76 | [21 empty] | 12143.6
Evaluate and Close Project - Handoff to Operations | [7 empty] | 12061.76 | [20 empty] | 12061.76
Operations Expenses
Program Management Oversight - 5 Years | [7 empty] | 17765.2 | 50206 | 50978.4 | 50206 | 50206 | 50206 | 50206 | 50206 | 50206 | 50206 | 50206 | 50978.4 | 49433.6 | 50206 | 50978.4 | 50978.4 | 50206 | 50206 | 50978.4 | 50978.4 | 32440.8 | 1007982
Help Desk Support Operations - 5 years | [7 empty] | 25204.32 | 71229.6 | 72325.44 | 71229.6 | 71229.6 | 71229.6 | 71229.6 | 71229.6 | 71229.6 | 71229.6 | 71229.6 | 72325.44 | 70133.76 | 71229.6 | 72325.44 | 72325.44 | 71229.6 | 71229.6 | 72325.44 | 72325.44 | 46025.28 | 1430071.2
Training Operations - 5 Years | [7 empty] | 19719.28 | 55728.4 | 56585.76 | 55728.4 | 55728.4 | 55728.4 | 55728.4 | 55728.4 | 55728.4 | 55728.4 | 55728.4 | 56585.76 | 54871.04 | 55728.4 | 56585.76 | 56585.76 | 55728.4 | 55728.4 | 56585.76 | 56585.76 | 36009.12 | 1118854.8
Maintenance Operations - 5 Years | [7 empty] | 39129.44 | 110583.2 | 112284.48 | 110583.2 | 110583.2 | 110583.2 | 110583.2 | 110583.2 | 110583.2 | 110583.2 | 110583.2 | 112284.48 | 108881.92 | 110583.2 | 112284.48 | 112284.48 | 110583.2 | 110583.2 | 112284.48 | 112284.48 |  | 2148716.64
Audit Program | [7 empty] | 8000 |  |  |  | 8000 |  |  |  | 8000 |  |  |  | 8000 |  |  |  | 8000 |  |  |  |  | 40000
Cumulative Expenses | 27254.62 | 168221.8 | 383518.68 | 529901.98 | 695499.74 | 862586.97 | 1088398.65 | 1291743.05 | 1579490.25 | 1871664.33 | 2159411.53 | 2455158.73 | 2742905.93 | 3030653.13 | 3318400.33 | 3614147.53 | 3901894.73 | 4189641.93 | 4481816.01 | 4773136.33 | 5060883.53 | 5353057.61 | 5645231.69 | 5940978.89 | 6228726.09 | 6520900.17 | 6813074.25 | 6927549.45 | 91655847.93 | Cum Est Cost
Overhead | 6813.655 | 42055.45 | 95879.67 | 132475.495 | 173874.935 | 215646.7425 | 272099.6625 | 322935.7625 | 394872.5625 | 467916.0825 | 539852.8825 | 613789.6825 | 685726.4825 | 757663.2825 | 829600.0825 | 903536.8825 | 975473.6825 | 1047410.4825 | 1120454.0025 | 1193284.0825 | 1265220.8825 | 1338264.4025 | 1411307.9225 | 1485244.7225 | 1557181.5225 | 1630225.0425 | 1703268.5625 | 1731887.3625 | 22913961.9825 | + O/H
Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2160000 | 2527200 | 2956824 | 3459484.08 | 4047596.3736 | 4735687.7571 | 5540754.6758 | 6482682.9707 | 7584739.0757 | 8874144.7186 | 10382749.3208 | 12147816.7053 | 14212945.5452 | 16629146.2879 | 19456101.1568 | 22763638.3535 | 26633456.8736 | 31161144.5421 | 36458539.1142 | 240214651.5509 | +Profits
Cumulative Revenues | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218003.3446 | 663386.2633 | 1245630.5582 | 1982469.0632 | 2907724.3061 | 4056644.9083 | 5456494.6928 | 7156405.9327 | 9202922.6754 | 11670193.5443 | 14612513.141 | 18117114.0611 | 22501707.7296 | 125644841.6384 | Grand Total
[29 empty] | 52.31% | Profit Margin