## Slide 1: Andrews’s Surprise Birthday Party

## Slide 2: What (Zaur)
What are we creating?
Balloons.
Birthday cake.
Ice cream cone cupcakes.
Gift wrappers.
Other birthday decorations.
Barbecued beef.
What activities must we do?
Send invitations.
Book a DJ.
Decorate the house.
Bake the birthday cake.
Purchase the cupcakes.
Purchase gifts and gift wrappers.
Barbecue the meat.
Invite guests.
Lure the birthday honouree away from the house for the most of the day.
Shout “surprise!” when the honouree arrives.
Serve the cupcakes and drinks to the guests.
Cut the birthday cake.
Open gifts.

## Slide 3: Timeline
What order must we do ?
1. Send invitation Cards. (Two weeks before the party)
2. Book the music DJ. (Two weeks before the party.)
3. Lure the honouree away from the house. (As soon as the honouree takes breakfast.)
4. Purchase drinks, cupcakes, balloons, decorators, party candles, beef, gifts and gift wrappers. (Between 9 and 10 am.)
5. Decorate the house. (Between 10 am and 1 pm.)
6. Prepare and bake the birthday cake. (Between 1 and 3 pm.)
7. Barbecue the beef. (Between 3 and 3.30 pm)
8. Call and welcome the guests. (Between 3.30 and 5 pm)
9. Serve the guests. (Between 5 and 7 pm.)
10. Shout “surprise!” when the honouree arrives. (Around 5.30 pm.)
11. Blow the candles and cut the cake as we sing Happy Birthday. (Around 5. 35 pm)
12. Open gifts (Between 6.30 and 7.30 pm)

## Slide 4: Overall Cost
How much will the activities cost?
Sending invitations – £1500
Birthday Cake ingredients – £200
Gifts and wrappers – £3200
Party Candles – £10
Party theme decorators – £3000
Drinks and cupcakes – £1550
Music DJ – £3500
Beef - £210
Misc. - £830

## Slide 5: Beautiful vs Horrible
What could go beautifully?
All the guests attend.
All required items available.
Preparations go according to plan.
What could go horribly wrong?
Guests attend in bigger numbers than expected.
The food becomes horrible, for instance, the cake is over baked or the beef is undercooked.
The drinks run out.
It becomes rainy.
The DJ becomes committed elsewhere at the last minutes.

## Slide 6: Risk Register: Guest
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
Brawl | 1.3 | 1 | 3 | 3 | Don’t invite reckless people | Calling in security/ police |  | 
Guest things the party is boring | 1.2 | 1 | 3 | 3 | Provide liquor | List of games that could be played |  | 

## Slide 7: Risk Register: Guest
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
More guests than expected. | 1.1 | 2 | 2 | 4 | Remind Guests About the party. Confirm attendance. | Use the misc. money to purchase more cupcakes and drinks. | Guests bringing relatives that were not in the plan. | Guests have not confirmed how many friends they would bring.
Less guests than expected. | 1.2 | 2.5 | 1.4 | 3.5 | Remind Guests About the party. Confirm attendance. | Request the attending guests to make the party livelier. | Weather changes. Traffic. Other last minute changes in plans. | No confirmation received on potential changes in the plan

## Slide 8: Risk Register: Food
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
Not enough food | 2.1 | 2 | 2 | 4 | Order more food | Order Take Out | Heidy | 30 mins
Allergic reactions | 2.2 | 1 | 2 | 2 | Label the food with care | Call NHS and prepare first aid kit | Heidy | 30 mins
Spoiled Food | 2.3 | 2 | 2 | 4 | Store food in a freezer | Order Take out | Heidy | 30 mins

## Slide 9: Risk Register: Food
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
Wrongly barbecued beef. | 2.1 | 1 | 2.9 | 2.9 | Close manning of the grill. | Buy more cupcakes to cover up for the bad meat. | Overcooking or undercooking. | The grill is not closely monitored.
Wrongly baked cake. | 2.2 | 1 | 3 | 3 | Follow the recipe’s instruction closely. | Order a ready-made cake from the nearest bakery. | Over baking or mixing ingredients wrongly. | Recipe is not carefully followed.

## Slide 10: Risk Register: Drinks
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
Running out of drinks | 3.1 | 2 | 2.5 | 5 | Monitoring the drinks to ensure it is noted before the last two or three bottles. | Order more drinks from the nearest store. | More than expected number of guests. | All the bottles are empty.

## Slide 11: Risk Register: Weather
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
Rain | 4.1 | 3 | 2 | 6 | Have an indoor section of the party | Indoor set up | Gloria | 
Snow | 4.2 | 2 | 3 | 6 | All set up indoors | Indoor set up | Gloria | 
Earthquake/ Natural Disasters | 4.3 | 1 | 3 | 3 | Earthquake safety Training | N/A | Gloria | 

## Slide 12: Risk Register: Music
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
The DJ gets committed elsewhere. | 5.1 | 1.2 | 2 | 2.4 | Confirm DJ’s schedule frequently | Use the family’s music playlist. | Lack of communication. | The DJ gets a better contract on that day and taking it because of failure of communication.

## Slide 13: Risk Register: Budgetary Control
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
Overspending of funds | 7.1 | 2 | 2 | 4 | Regular systematic budget monitoring and control. | Communicate to organisers (family) and negotiate. | Planning financial team. | Before event, preferably.
Immense underspending of funds | 7.2 | 2 | 1 | 3 | Regular systematic budget monitoring and control. | Communicate to organisers (family) and negotiate. | Planning financial team. | Before event, preferably.

## Slide 14: Risk Register: Contractual Arrangements
Nature of Risk | Risk No | Probability (P) (1-3) | Impact (I) (1-3) | Risk Score (P x I) | Mitigation | Contingency | Action by | Action when
Catering – no show | 6.1 | 1 | 3 | 3 | Selection of a catering firm with well-established name. Periodic communication and affirmation with supplier. | Last-minute catering or home delivery (sushi, platters, cupcakes, etc.). Last-minute catering may go beyond budget. | Host or member of the project team. | Either 45min lateness after expected start time or ASAP when communicated from the caterer.
Catering - miscommunication regarding menus | 6.2 | 2 | 2 | 4 | Regular contact with catering enterprise. | Communicate to organisers (family) and adjust invoices with caterer. | Managing team. | Pre-communicated or on implementation