Student’s Name

Institutional Affiliation

Course Name

Instructor’s Name

| Task | Start time |  | Completion time | duration |
| --- | --- | --- | --- | --- |
| Initiation | Week 1 |  | Week3 | 3 weeks |
| First meeting of team leaders | week 1 |  | week 1 | I week |
| Mission statement | Week 1 |  | Week 3 | 2 weeks |
| Team member selection and team leader | Week2 |  | Week 3 | I week |
| Team orientation | Week 3 |  | Week 3 | 1 week |
| PLANNING | Week 3 |  | Week 6 | 3 weeks |
| Planning meeting to brainstorm and Identify problems | Week 2 |  | Week 2 | 1 week |
| Assign individuals tasks | Week 3 | Week 3 |  | 1 week |
| FEMA coordination planning | Week 3 | Week 8 |  | 5 weeks |
| Admission and medical information management | Week 3 | Week5 |  | 2 weeks |
| Equipment storage and access | Week 2 | Week 5 |  | 3 weeks |
| Infection management | Week 2 | Week 5 |  | 3 weeks |
| Identify locations suitable for patients | Week 2 | Week 5 |  | 3 weeks |
| HVAC issues | Week 2 | Week 5 |  | 3 weeks |
| Media management | Week 2 | Week 5 |  | 3 weeks |
| Develop training plan | Week 3 | Week 6 |  | 3 weeks |
| EXECUTION | Week 5 | Week 10 |  | 5 weeks |
| Collection team input and write the final plan | Week 5 | Week 8 |  | 3 weeks |
| Training | Week 4 | Week 9 |  | 5 weeks |
| CLOSURE | Week 8 | Week 12 |  | 4weeks |
| Submit plan for federal funding | Week 10 | Week 10 |  | O weeks |
| Rehearsal exercise | Week 10 | Week 10 |  | O weeks |
| Prepare and submit final document | Week 10 | Week 12 |  | 2 weeks |
| Begin on going evaluation | Week 12 | Week 12 |  | 0 weeks |

QUESTION 2

From the case study, the following are representatives of different healthcare departments: hospital administrator, health information officers, emergence services providers, media officials, government represented by county health officer, hospital staffs, procurement officers and database analysts .During project evaluation and performance, all stakeholders must be engaged purposely to contribute for the success of the project. Each agency should be fully represented from the initiation stage upto the closure stage if the objective of the project must be met for maximum benefit of all the parties involved. These representatives are chosen to represent each healthcare departments’ needs to ensure each unit department will derive maximum return or benefits of the project.

QUESTION 3

Some of the individuals who should be represented in this team project may include: doctors, nurses, dentists, administrative and support staffs, community health workers and patients, physician assistants, pharmacists and technologists. These are very important stakeholders who should be involved in this project team .These individuals should be involved since they are determinants the quality of health care consumed by the general public. One of the key determinants of quality of healthcare consumed is personnel involved in administering health which is provided by these individuals. Furthermore, the following illustration will depict why the listed individuals should be involved in this team project. Whenever patients visit primary care providers, administrative staff traces the medical records, greets the patients and makes call reminders as well verifying patient’s insurance covers .nurses measures the patient weight and the detectable signs and symptoms before escorting the patient to the examination room. Medical financial expert’s bills the patient’s insurance for the health care providers .This clearly demonstrates why it’s important to indicate health care providers in this project team.

QUESTION 4

The project team should ensure all the departments of health must be fully represented these departments may include; outpatient department, inpatient service, medical department, nursing department, paramedical department, medical record department and physical medicine and rehabilitation department.

Outpatient department carries out medical guidelines and tests that are carried out daily .these services are; counseling, diagnosis services like lab tests. The attendants of this department have enough counseling skills and knowledge that is aimed at ensuring that patients are encouraged to enjoy the services. Inpatient service is another critical department of health care main role is to conduct admissions of the patient. This department should be run database expertise and data analysts who have the capacity to main patient’s records.

Moreover, the medical department is also mandated to conduct community outreach and education and prevention and wellness of patient and this department should be equipped with medical professionals. The nursing department assesses both patients and staff, identify issues, problems. The department is also mandated to develop a plan as well as the implementation thus planners should be employed to ensure its success.

In conclusion, all the departments of health care must be equipped with relevant expertise with skills based applications in each department to ensure each department delivers best as per the expectations of patients.

References

Pagana, K. D., Pagana, T. J., & Pagana, T. N. (2019). Mosby’s diagnostic and laboratory test reference (14th ed.). Elsevier.

Francisco Department of Public Health. (2016). San Francisco community health needs assessment 2016. https://www.sfdph.org/dph/hc/HCAgen/HCAgen2016/May%2017/2016CHNA-2.pdf

Healthcare Infection Control Practices Advisory Committee. (2009). Catheter-associated urinary tract infections (CAUTI). U.S. Department of Health & Human Services, Centers for Disease Control and Prevention. https://www.cdc.gov/infectioncontrol/guidelines/cauti/index.html