## 9-39 a
Network Analysis |  |  | Minimum Spanning Tree
Start node | 1
Data |  |  |  | Results
Branch name | Start node | End node | Cost | Include | Cost
Branch 1 | 1 | 2 | 5 | 1 | 5
Branch 2 | 1 | 3 | 6 | 1 | 6
Branch 3 | 1 | 4 | 6 | 1 | 6
Branch 4 | 1 | 5 | 5 | 1 | 5
Branch 5 | 2 | 6 | 7
Branch 6 | 3 | 7 | 5 | 1 | 5
Branch 7 | 4 | 7 | 7
Branch 8 | 5 | 8 | 4 | 1 | 4
Branch 9 | 6 | 7 | 1 | 1 | 1
Branch 10 | 7 | 9 | 6
Branch 11 | 8 | 9 | 2 | 1 | 2
|  |  |  | Sum | 34
Iterations |  |  |  | a. the least expensive way to run cable to the houses? |  | 2
Branch 1 | 1 | 2 | 5
Branch 4 | 1 | 5 | 5
Branch 8 | 5 | 8 | 4
Branch 11 | 8 | 9 | 2
Branch 2 | 1 | 3 | 6
Branch 6 | 3 | 7 | 5
Branch 9 | 6 | 7 | 1
Branch 3 | 1 | 4 | 6
Solve
Enter the start node, end node and cost for each branch and then press the Solve button.
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A6: Network Analysis: Submodel = 0; Problem size @ 11 by 3

## 9-39 b
Network Analysis |  |  | Minimum Spanning Tree
Start node | 1
Data |  |  |  | Results
Branch name | Start node | End node | Cost | Include | Cost
Branch 1 | 1 | 2 | 5 | 1 | 5
Branch 2 | 1 | 3 | 1 | 1 | 1
Branch 3 | 1 | 4 | 1 | 1 | 1
Branch 4 | 1 | 5 | 1 | 1 | 1
Branch 5 | 2 | 6 | 7
Branch 6 | 3 | 7 | 5 | 1 | 5
Branch 7 | 4 | 7 | 7
Branch 8 | 5 | 8 | 4 | 1 | 4
Branch 9 | 6 | 7 | 1 | 1 | 1
Branch 10 | 7 | 9 | 6
Branch 11 | 8 | 9 | 2 | 1 | 2
|  |  |  | Sum | 20
Iterations |  |  |  | the alteration of the costs has an effect of reducing the initial final cost from 34 to 20.
Branch 2 | 1 | 3 | 1
Branch 3 | 1 | 4 | 1
Branch 4 | 1 | 5 | 1
Branch 8 | 5 | 8 | 4
Branch 11 | 8 | 9 | 2
Branch 1 | 1 | 2 | 5
Branch 6 | 3 | 7 | 5
Branch 9 | 6 | 7 | 1
Solve
Enter the start node, end node and cost for each branch and then press the Solve button.
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A6: Network Analysis: Submodel = 0; Problem size @ 11 by 3

## 9-40 a
Network Analysis |  |  | Shortest Path
Origin | 1
Destination | 8
Data | Undirected network
Branch name | Start node | End node | Distance
Branch 1 | 1 | 2 | 3
Branch 2 | 1 | 3 | 2 |  |  | the shortest distance is 12 which is of branch 9 from start node 1 to 3 to 5 to 7 to 6 and 8.
Branch 3 | 2 | 4 | 3
Branch 4 | 3 | 5 | 3
Branch 5 | 4 | 5 | 1
Branch 6 | 4 | 6 | 4
Branch 7 | 5 | 7 | 2
Branch 8 | 6 | 7 | 2
Branch 9 | 6 | 8 | 3
Branch 10 | 7 | 8 | 6
Results
Branch | Start node | End node | Cost | Cumulative distance
2 | 1 | 3 | 2 | 2
4 | 3 | 5 | 3 | 5
7 | 5 | 7 | 2 | 7
8 | 7 | 6 | 2 | 9
9 | 6 | 8 | 3 | 12
Distance Table | Node 1 | Node 2 | Node 3 | Node 4 | Node 5 | Node 6 | Node 7 | Node 8
Node 1 | 0 | 3 | 2 | 6 | 5 | 9 | 7 | 12
Node 2 | 3 | 0 | 5 | 3 | 4 | 7 | 6 | 10
Node 3 | 2 | 5 | 0 | 4 | 3 | 7 | 5 | 10
Node 4 | 6 | 3 | 4 | 0 | 1 | 4 | 3 | 7
Node 5 | 5 | 4 | 3 | 1 | 0 | 4 | 2 | 7
Node 6 | 9 | 7 | 7 | 4 | 4 | 0 | 2 | 3
Node 7 | 7 | 6 | 5 | 3 | 2 | 2 | 0 | 5
Node 8 | 12 | 10 | 10 | 7 | 7 | 3 | 5 | 0
Solve
Enter the start node, end node and distance for each branch and then press the Solve button. You may use any node as the origin or destination. The default values used are the lowest and highest node numbers. In an undirected network distances from end node to start node are the same as from the start node to the end node. In a directed network the arc from end node to start node is not automatic and must be entered by the user.
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A6: Network Analysis: Submodel = 0; Problem size @ 10 by 0

## 9-40 b
Network Analysis |  |  | Shortest Path
Origin | 1
Destination | 8
Data | Undirected network
Branch name | Start node | End node | Distance
Branch 1 | 1 | 2 | 3
Branch 2 | 1 | 3 | 2 |  |  | The shortest route now has a distance of 10 and it passes through nodes 1 to 3 to 5 to 7 to 6 and 8. the new distances have shortened the distance from 1 to 8 by 2
Branch 3 | 2 | 4 | 3
Branch 4 | 3 | 5 | 1
Branch 5 | 4 | 5 | 1
Branch 6 | 4 | 6 | 4
Branch 7 | 5 | 7 | 2
Branch 8 | 6 | 7 | 2
Branch 9 | 6 | 8 | 3
Branch 10 | 7 | 8 | 6
Results
Branch | Start node | End node | Cost | Cumulative distance
2 | 1 | 3 | 2 | 2
4 | 3 | 5 | 1 | 3
7 | 5 | 7 | 2 | 5
8 | 7 | 6 | 2 | 7
9 | 6 | 8 | 3 | 10
Distance Table | Node 1 | Node 2 | Node 3 | Node 4 | Node 5 | Node 6 | Node 7 | Node 8
Node 1 | 0 | 3 | 2 | 4 | 3 | 7 | 5 | 10
Node 2 | 3 | 0 | 5 | 3 | 4 | 7 | 6 | 10
Node 3 | 2 | 5 | 0 | 2 | 1 | 5 | 3 | 8
Node 4 | 4 | 3 | 2 | 0 | 1 | 4 | 3 | 7
Node 5 | 3 | 4 | 1 | 1 | 0 | 4 | 2 | 7
Node 6 | 7 | 7 | 5 | 4 | 4 | 0 | 2 | 3
Node 7 | 5 | 6 | 3 | 3 | 2 | 2 | 0 | 5
Node 8 | 10 | 10 | 8 | 7 | 7 | 3 | 5 | 0
Solve
Enter the start node, end node and distance for each branch and then press the Solve button. You may use any node as the origin or destination. The default values used are the lowest and highest node numbers. In an undirected network distances from end node to start node are the same as from the start node to the end node. In a directed network the arc from end node to start node is not automatic and must be entered by the user.
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A6: Network Analysis: Submodel = 0; Problem size @ 10 by 0

## 9-41 a
Network Analysis |  |  | Maximal Flow
Source | 1
Sink
Data |  |  |  |  | Results
Branch name | Start node | End node | Capacity | Reverse Capacity | Flow
Branch 1 | 1 | 2 | 10 | 4 | 10
Branch 2 | 1 | 3 | 8 | 2 | 5
Branch 3 | 2 | 4 | 12 | 1 | 10
Branch 4 | 2 | 5 | 6 | 6
Branch 5 | 3 | 5 | 8 | 1 | 5
Branch 6 | 4 | 6 | 10 | 2 | 10
Branch 7 | 5 | 6 | 10 | 10
Branch 8 | 5 | 7 | 5 | 5 | 5
Branch 9 | 6 | 8 | 10 | 1 | 10
Branch 10 | 7 | 8 | 10 | 1 | 5
[5 empty] | 15 | Maximum network flow
Iterations
a. the maximum flow is 15
1-> 2-> 4-> 6-> 8
1-> 3-> 5-> 7-> 8
Solve
Enter the start node, end node capacity and reverse capacity for each branch and then press the Solve button. You may use any node as the source or sink. The default values used are the lowest and highest node numbers.
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A6: Network Analysis: Submodel = 0; Problem size @ 10 by 0

## 9-41 b
Network Analysis |  |  | Maximal Flow
Source | 1
Sink
Data | [5 empty] | Results
Branch name | Start node | End node | Capacity | Reverse Capacity |  | Flow
Branch 1 | 1 | 2 | 10 | 4 |  | 10
Branch 2 | 1 | 3 | 8 | 2 |  | 5
Branch 3 | 2 | 4 | 12 | 1 |  | 10
Branch 4 | 2 | 5 | 0 | 0
Branch 5 | 3 | 5 | 8 | 1 |  | 5
Branch 6 | 4 | 6 | 10 | 2 |  | 10
Branch 7 | 5 | 6 | 10 | 10
Branch 8 | 5 | 7 | 5 | 5 |  | 5
Branch 9 | 6 | 8 | 10 | 1 |  | 10
Branch 10 | 7 | 8 | 10 | 1 |  | 5
[6 empty] | 15 | Maximum network flow
Iterations
1-> 2-> 4-> 6-> 8 |  |  |  |  | b. it does not have any effect since the maximum network flow is same.
1-> 3-> 5-> 7-> 8
Solve
Enter the start node, end node capacity and reverse capacity for each branch and then press the Solve button. You may use any node as the source or sink. The default values used are the lowest and highest node numbers.
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A6: Network Analysis: Submodel = 0; Problem size @ 10 by 0

## 11-18
Project Management |  |  | Precedences; 3 time estimates
Data |  |  |  |  | a. expected durations and variance
Activity | Optimistic | Likely | Pessimistic |  | Mean | Std dev | Variance
A | 3 | 6 | 9 |  | 6 | 1 | 1
B | 2 | 4 | 6 |  | 4 | 0.66667 | 0.44444
C | 1 | 2 | 3 |  | 2 | 0.33333 | 0.11111
D | 6 | 7 | 8 |  | 7 | 0.33333 | 0.11111
E | 2 | 4 | 6 |  | 4 | 0.66667 | 0.44444
F | 6 | 10 | 14 |  | 10 | 1.3333 | 1.7778
G | 1 | 2 | 6 |  | 2.5 | 0.83333 | 0.69444
H | 3 | 6 | 9 |  | 6 | 1 | 1
I | 10 | 11 | 12 |  | 11 | 0.33333 | 0.11111
J | 14 | 16 | 21 |  | 16.5 | 1.1667 | 1.3611
K | 2 | 8 | 11 |  | 7.5 | 1.5 | 2.25
Precedences |  | Immediate Predecessors (1 per column)
Activity | Time | Pred 1 | Pred 2
A | 6
B | 4 |  |  |  |  | probability of finishing before 38 days
C | 2 |  |  |  |  | mean= | 36.5
D | 7 | C |  |  |  | std dev= | 2.3863
E | 4 | B | D |  |  | no of days= | 38
F | 10 | A | E |  |  | z-score = | 0.62859
G | 2.5 | A | E |  |  | probability = | 0.73519
H | 6 | F
I | 11 | G
J | 16.5 | G
K | 7.5 | H | I
Results
Activity | Early Start | Early Finish | Late Start | Late Finish | Slack |  | Variance | Critical Variance
A | 0 | 6 | 7 | 13 | 7 |  | 1
B | 0 | 4 | 5 | 9 | 5 |  | 0.44444
C | 0 | 2 | 0 | 2 | 0 |  | 0.11111 | 0.11111
D | 2 | 9 | 2 | 9 | 0 |  | 0.11111 | 0.11111
E | 9 | 13 | 9 | 13 | 0 |  | 0.44444 | 0.44444
F | 13 | 23 | 13 | 23 | 0 |  | 1.7778 | 1.7778
G | 13 | 15.5 | 15.5 | 18 | 2.5 |  | 0.69444
H | 23 | 29 | 23 | 29 | 0 |  | 1 | 1
I | 15.5 | 26.5 | 18 | 29 | 2.5 |  | 0.11111
J | 15.5 | 32 | 20 | 36.5 | 4.5 |  | 1.3611
K | 29 | 36.5 | 29 | 36.5 | 0 |  | 2.25 | 2.25
| Project | 36.5 |  |  |  |  | Project | 5.6944
[7 empty] | Std.dev | 2.3863
Early start computations
A |  | 0 | 0
B |  | 0 | 0
C |  | 0 | 0
D |  | 2 | 0
E |  | 4 | 9
F |  | 6 | 13
G |  | 6 | 13
H |  | 23 | 0
I |  | 15.5 | 0
J |  | 15.5 | 0
K |  | 29 | 26.5
Late finish computations
| A | B | C | D | E | F | G | H | I | J | K
A | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
B | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
C | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
D | 36.5 | 36.5 | 2 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
E | 36.5 | 9 | 36.5 | 9 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
F | 13 | 36.5 | 36.5 | 36.5 | 13 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
G | 15.5 | 36.5 | 36.5 | 36.5 | 15.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
H | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 23 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
I | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 18 | 36.5 | 36.5 | 36.5 | 36.5
J | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 20 | 36.5 | 36.5 | 36.5 | 36.5
K | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 29 | 29 | 36.5 | 36.5
| 13 | 9 | 2 | 9 | 13 | 23 | 18 | 29 | 29 | 36.5 | 36.5
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A4: Project Management: Submodel = 2; Problem size @ 11 by 2
Note on A17: Project Management: Submodel = 2; Problem size @ 11 by 2
Enter the times in the appropriate column(s). Enter the precedences, one per column. (Do not use commas).

## 11-19
Project Management |  |  | Precedences; 3 time estimates
Data
Activity | Optimistic | Likely | Pessimistic |  | Mean | Std dev | Variance
A | 3 | 6 | 6 |  | 5.5 | 0.5 | 0.25
B | 5 | 8 | 11 |  | 8 | 1 | 1
C | 5 | 6 | 10 |  | 6.5 | 0.83333 | 0.69444
D | 1 | 2 | 6 |  | 2.5 | 0.83333 | 0.69444
E | 7 | 11 | 15 |  | 11 | 1.3333 | 1.7778
F | 7 | 9 | 14 |  | 9.5 | 1.1667 | 1.3611
G | 6 | 8 | 10 |  | 8 | 0.66667 | 0.44444
H | 3 | 4 | 8 |  | 4.5 | 0.83333 | 0.69444
I | 3 | 5 | 7 |  | 5 | 0.66667 | 0.44444
Precedences |  | Immediate Predecessors (1 per column)
Activity | Time | Pred 1 | Pred 2 | Pred 3
A | 5.5
B | 8 | A |  |  |  | d. | Project will take 34 or less |  |  | e. will take longer than 29
C | 6.5 | A |  |  |  | mean | 35 |  |  | mean | 35
D | 2.5 | B | C |  |  | std.dev | 2.1082 |  |  | std.dev | 2.1082
E | 11 | D |  |  |  | time | 34 |  |  | time | 29
F | 9.5 | D |  |  |  | z-score | -0.47434 |  |  | z-score | -2.846
G | 8 | D |  |  |  | probability | 0.31763 |  |  | probability | 0.99779
H | 4.5 | F | G |  |  |  | chances project will take 34 or less days is 0.1376 |  |  | chances project will take longer than 29 days is 0.9978
I | 5 | E | F | H
Results
Activity | Early Start | Early Finish | Late Start | Late Finish | Slack |  | Variance | Critical Variance
A | 0 | 5.5 | 0 | 5.5 | 0 |  | 0.25 | 0.25
B | 5.5 | 13.5 | 5.5 | 13.5 | 0 |  | 1 | 1
C | 5.5 | 12 | 7 | 13.5 | 1.5 |  | 0.69444
D | 13.5 | 16 | 13.5 | 16 | 0 |  | 0.69444 | 0.69444
E | 16 | 27 | 19 | 30 | 3 |  | 1.7778
F | 16 | 25.5 | 16 | 25.5 | 0 |  | 1.3611 | 1.3611
G | 16 | 24 | 17.5 | 25.5 | 1.5 |  | 0.44444
H | 25.5 | 30 | 25.5 | 30 | 0 |  | 0.69444 | 0.69444
I | 30 | 35 | 30 | 35 | 0 |  | 0.44444 | 0.44444
| Project | 35 |  |  |  |  | Project | 4.4444
[7 empty] | Std.dev | 2.1082
Early start computations
A |  | 0 | 0 | 0
B |  | 5.5 | 0 | 0
C |  | 5.5 | 0 | 0
D |  | 13.5 | 12 | 0
E |  | 16 | 0 | 0
F |  | 16 | 0 | 0
G |  | 16 | 0 | 0
H |  | 25.5 | 24 | 0
I |  | 27 | 25.5 | 30
Late finish computations
| A | B | C | D | E | F | G | H | I
A | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
B | 5.5 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
C | 7 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
D | 35 | 13.5 | 13.5 | 35 | 35 | 35 | 35 | 35 | 35
E | 35 | 35 | 35 | 19 | 35 | 35 | 35 | 35 | 35
F | 35 | 35 | 35 | 16 | 35 | 35 | 35 | 35 | 35
G | 35 | 35 | 35 | 17.5 | 35 | 35 | 35 | 35 | 35
H | 35 | 35 | 35 | 35 | 35 | 25.5 | 25.5 | 35 | 35
I | 35 | 35 | 35 | 35 | 30 | 30 | 35 | 30 | 35
| 5.5 | 13.5 | 13.5 | 16 | 30 | 25.5 | 25.5 | 30 | 35
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A4: Project Management: Submodel = 2; Problem size @ 9 by 3
Note on A15: Project Management: Submodel = 2; Problem size @ 9 by 3
Enter the times in the appropriate column(s). Enter the precedences, one per column. (Do not use commas).

## 11-35
Project Management |  |  | Crashing
Results
Data |  |  |  | Normal time | 17 | [5 empty] | Minimum crash cost to meet project goal | 700
Project goal | 16 |  |  | Minimum time | 10 | [5 empty] | Project time | 16
[5 empty] | Immediate Predecessors (1 per column) | [5 empty] | Intermediate Computations
Activity | Normal Time (weeks) | Crash Time (weeks) | Normal Cost | Total Cost with Crashing | Pred 1 | Pred 2 | Pred 3 | Pred 4 |  | Crash days | Crash cost/day | Crash limit
A | 3 | 2 | 8000 | 9800 | [5 empty] | 0 | 1800 | 1
B | 4 | 3 | 9000 | 10000 | [5 empty] | 0 | 1000 | 1
C | 6 | 4 | 12000 | 15000 | A |  |  |  |  | 0 | 1500 | 2
D | 2 | 1 | 15000 | 15500 | B |  |  |  |  | 0 | 500 | 1
E | 5 | 3 | 5000 | 8700 | A |  |  |  |  | 0 | 1850 | 2
F | 2 | 1 | 7500 | 9000 | C |  |  |  |  | 0 | 1500 | 1
G | 4 | 2 | 8000 | 9400 | D | E |  |  |  | 1 | 700 | 2
H | 5 | 3 | 5000 | 6600 | F | G |  |  |  | 0 | 800 | 2
[10 empty] | 0 | 0 | 0
Precedence computations | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 if col precedes row | A | B | C | D | E | F | G | H | xxxxx
A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
G | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
H | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Normal time | 3 | 4 | 6 | 2 | 5 | 2 | 4 | 5 | 0
TimeFinish (variable) | 3 | 6 | 9 | 8 | 8 | 11 | 11 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
crash days (variable) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
limit | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project time | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crash days | Finish Times for Tasks must be greater than finish for all predecessors | Finish A + T(row)-crash row | Finish B + T(row)-crash row | Finish C + T(row)-crash row | Finish D + T(row)-crash row | Finish E + T(row)-crash row | Finish F + T(row)-crash row | Finish G + T(row)-crash row
0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
0 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
0 | 9 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 6
0 | 8 | 2 | 8 | 2 | 2 | 2 | 2 | 2 | 2
0 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5
0 | 11 | 2 | 2 | 11 | 2 | 2 | 2 | 2 | 2
1 | 11 | 3 | 3 | 3 | 11 | 11 | 3 | 3 | 3
0 | 16 | 5 | 5 | 5 | 5 | 5 | 16 | 16 | 5
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | A: 3; B: 0; C: 0; D: 0; E: 0
B | A: 4; B: 0; C: 0; D: 0; E: 0
C | A: 6; B: A; C: 0; D: 0; E: 0
D | A: 2; B: B; C: 0; D: 0; E: 0
E | A: 5; B: A; C: 0; D: 0; E: 0
F | A: 2; B: C; C: 0; D: 0; E: 0
G | A: 4; B: D; C: E; D: 0; E: 0
H | A: 5; B: F; C: G; D: 0; E: 0
Results
Task | A: Early Start; B: Early Finish
A | A: 0; B: 3
B | A: 0; B: 4
C | A: 3; B: 9
D | A: 4; B: 6
E | A: 3; B: 8
F | A: 9; B: 11
G | A: 8; B: 12
H | A: 12; B: 17
| Project | 17
Early start computations
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 3; C: 0; D: 0; E: 0
D | B: 4; C: 0; D: 0; E: 0
E | B: 3; C: 0; D: 0; E: 0
F | B: 9; C: 0; D: 0; E: 0
G | B: 6; C: 8; D: 0; E: 0
H | B: 11; C: 12; D: 0; E: 0
Late finish computations
| A | B | C | D | E | F | G | H
A | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
B | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
C | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
D | 17 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 17
E | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
F | 17 | 17 | 0 | 17 | 17 | 17 | 17 | 17 | 17
G | 17 | 17 | 17 | 0 | 0 | 17 | 17 | 17 | 17
H | 17 | 17 | 17 | 17 | 17 | 0 | 0 | 17 | 17
| 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0
Project Management
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | 2 | 0 | 0 | 0 | 0
B | 3 | 0 | 0 | 0 | 0
C | 4 | A | 0 | 0 | 0
D | 1 | B | 0 | 0 | 0
E | 3 | A | 0 | 0 | 0
F | 1 | C | 0 | 0 | 0
G | 2 | D | E | 0 | 0
H | 3 | F | G | 0 | 0
Results | D: 0
Task | Early Start | Early Finish | Late Start | Late Finish | Slack
A | 0 | 2 | -2 | 0 | -2
B | 0 | 3 | -3 | 0 | -3
C | 2 | 6 | -4 | 0 | -6
D | 3 | 4 | -1 | 0 | -4 |  | 1 | 3
E | 2 | 5 | -3 | 0 | -5
F | 6 | 7 | -1 | 0 | -7
G | 5 | 7 | -2 | 0 | -7
H | 7 | 10 | -3 | 0 | -10
| Project | 10
Early start computations
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 2; C: 0; D: 0; E: 0
D | B: 3; C: 0; D: 0; E: 0
E | B: 2; C: 0; D: 0; E: 0
F | B: 6; C: 0; D: 0; E: 0
G | B: 4; C: 5; D: 0; E: 0
H | B: 7; C: 7; D: 0; E: 0
Late finish computations
| A | B | C | D | E | F | G | H
A | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
B | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
C | -4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
D | 10 | -1 | 10 | 10 | 10 | 10 | 10 | 10 | 10
E | -3 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
F | 10 | 10 | -1 | 10 | 10 | 10 | 10 | 10 | 10
G | 10 | 10 | 10 | -2 | -2 | 10 | 10 | 10 | 10
H | 10 | 10 | 10 | 10 | 10 | -3 | -3 | 10 | 10
| 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
a. | A: the activities to be crushed are D and E at a total cost of 700
b. | A: the paths remaining after crush are: -
A-> B-> C->G->H
A-> C-> F->G->H
A-> B-> G->C->H
Enter the values in the shaded area then use the Run Excel's Solver button. Alternatively, open Solver by going to the Data Tab (Excel 2007, 2010, 2013, 2016) or the Tools menu (Excel 2003, 2011).
Run Excel's Solver
Solver Help
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A5: Project Management: Submodel = 3; Problem size @ 8 by 0

## 12-12
Waiting Lines |  | Single Server Model(M/M/1)
Data |  |  | Results
Arrival rate (l) | 10 |  | Average server utilization(r) | 0.83333
Service rate (m) | 12 |  | Average number of customers in the queue(Lq) | 4.1667
Number of servers | 1 |  | Average number of customers in the system(L) | 5
|  |  | Average waiting time in the queue(Wq) | 0.41667
|  |  | Average time in the system(W) | 0.5
|  |  | Probability (% of time) system is empty (P0) | 0.16667
the server model is M/M/1 since there is 1 server. The models arrial rate is 10 and service rate is 12
a. average number of cars in line |  | 4.1667
b. average time a car waits before it is washed |  | 0.41667
c. average time a car spends in the service system |  | 0.5
d. utilization rate of the car wash |  | 0.83333
e. probability there is no car in the system. |  | 0.16667
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A4: Waiting Lines: Submodel = 0; Problem size @ 2 by 2
The arrival RATE and service RATE both must be rates and use the same time unit. Given a time such as 10 minutes, convert it to a rate such as 6 per hour.

## 12-23
Waiting Lines |  | Multiple server model (M/M/s)
Sensitivity Table
Number of servers
Data |  |  | Results |  |  | 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Arrival rate (l) | 30 |  | Average server utilization(r) | 0.5 |  | 0.5 | NA | 0.75 | 0.5 | 0.375 | 0.3 | 0.25 | 0.21429 | 0.1875 | 0.16667 | 0.15
Service rate (m) | 20 |  | Average number of customers in the queue(Lq) | 0.23684 |  | 0.23684 | NA | 1.9286 | 0.23684 | 0.044751 | 0.0086311 | 0.0015685 | 0.00026255 | 4.0283e-05 | 5.6732e-06 | 7.3614e-07
Number of servers(s) | 3 |  | Average number of customers in the system(L) | 1.7368 |  | 1.7368 | NA | 3.4286 | 1.7368 | 1.5448 | 1.5086 | 1.5016 | 1.5003 | 1.5 | 1.5 | 1.5
Server cost $/time) | 300 |  | Average waiting time in the queue(Wq) | 0.0078947 |  | 0.0078947 | NA | 0.064286 | 0.0078947 | 0.0014917 | 0.0002877 | 5.2283e-05 | 8.7517e-06 | 1.3428e-06 | 1.8911e-07 | 2.4538e-08
Waiting cost ($/time) | 100 |  | Average time in the system(W) | 0.057895 |  | 0.057895 | NA | 0.11429 | 0.057895 | 0.051492 | 0.050288 | 0.050052 | 0.050009 | 0.050001 | 0.05 | 0.05
|  |  | Probability (% of time) system is empty (P0) | 0.21053 |  | 0.21053 | NA | 0.14286 | 0.21053 | 0.22099 | 0.22277 | 0.22307 | 0.22312 | 0.22313 | 0.22313 | 0.22313
|  |  | Cost - based on waiting | 923.6842 |  | 923.6842 | NA | 792.8571 | 923.6842 | 1204.4751 | 1500.8631 | 1800.1568 | 2100.0263 | 2400.004 | 2700.0006 | 3000.0001
|  |  | Cost - based on system | 1073.6842 |  | 1073.6842 | NA | 942.8571 | 1073.6842 | 1354.4751 | 1650.8631 | 1950.1568 | 2250.0263 | 2550.004 | 2850.0006 | 3150.0001
Probabilities
Number | Probability | Cumulative Probability |  | a. Average time in the line if clerks 2,3 and 4 are used |  | Number of servers 4: 0.0078947
0 | 0.21053 | 0.21053 |  | b. total time spent waiting in the line each day if 2, 3 and 4 clerks are used |  | Number of servers 5: 0.0078947
1 | 0.31579 | 0.52632 |  | c. total daily waiting costs |  | Number of servers 1: 923.6842
2 | 0.23684 | 0.76316 |  | dail service cost |  | 3: 1073.6842
3 | 0.11842 | 0.88158 |  | the minimumcost is 923.6842
4 | 0.059211 | 0.94079
5 | 0.029605 | 0.97039
6 | 0.014803 | 0.9852
7 | 0.0074013 | 0.9926
8 | 0.0037007 | 0.9963
9 | 0.0018503 | 0.99815
10 | 0.00092516 | 0.99907
11 | 0.00046258 | 0.99954
12 | 0.00023129 | 0.99977
13 | 0.00011565 | 0.99988
14 | 5.7823e-05 | 0.99994
15 | 2.8911e-05 | 0.99997
16 | 1.4456e-05 | 0.99999
17 | 7.2278e-06 | 0.99999
18 | 3.6139e-06 | 1
19 | 1.807e-06 | 1
20 | 9.0348e-07 | 1 | term2 | P0(s) | Rho(s) | 3: Lq(s); Number of servers 1: L(s); Number of servers 2: Wq(s); Number of servers 3: W(S)
0 | 1
1 | 1.5 | 1 | -3 | -0.5 | 1.5 | 3: -4.5; Number of servers 1: -3; Number of servers 2: -0.15; Number of servers 3: -0.1
2 | 1.125 | 2.5 | 4.5 | 0.14286 | 0.75 | 3: 1.9286; Number of servers 1: 3.4286; Number of servers 2: 0.064286; Number of servers 3: 0.11429
3 | 0.5625 | 3.625 | 1.125 | 0.21053 | 0.5 | 3: 0.23684; Number of servers 1: 1.7368; Number of servers 2: 0.0078947; Number of servers 3: 0.057895
4 | 0.21094 | 4.1875 | 0.3375 | 0.22099 | 0.375 | 3: 0.044751; Number of servers 1: 1.5448; Number of servers 2: 0.0014917; Number of servers 3: 0.051492
5 | 0.063281 | 4.3984 | 0.090402 | 0.22277 | 0.3 | 3: 0.0086311; Number of servers 1: 1.5086; Number of servers 2: 0.0002877; Number of servers 3: 0.050288
6 | 0.01582 | 4.4617 | 0.021094 | 0.22307 | 0.25 | 3: 0.0015685; Number of servers 1: 1.5016; Number of servers 2: 5.2283e-05; Number of servers 3: 0.050052
7 | 0.0033901 | 4.4775 | 0.0043146 | 0.22312 | 0.21429 | 3: 0.00026255; Number of servers 1: 1.5003; Number of servers 2: 8.7517e-06; Number of servers 3: 0.050009
8 | 0.00063564 | 4.4809 | 0.00078232 | 0.22313 | 0.1875 | 3: 4.0283e-05; Number of servers 1: 1.5; Number of servers 2: 1.3428e-06; Number of servers 3: 0.050001
9 | 0.00010594 | 4.4816 | 0.00012713 | 0.22313 | 0.16667 | 3: 5.6732e-06; Number of servers 1: 1.5; Number of servers 2: 1.8911e-07; Number of servers 3: 0.05
10 | 1.5891e-05 | 4.4817 | 1.8695e-05 | 0.22313 | 0.15 | 3: 7.3614e-07; Number of servers 1: 1.5; Number of servers 2: 2.4538e-08; Number of servers 3: 0.05
11 | 2.1669e-06 | 4.4817 | 2.5091e-06 | 0.22313 | 0.13636 | 3: 8.8398e-08; Number of servers 1: 1.5; Number of servers 2: 2.9466e-09; Number of servers 3: 0.05
12 | 2.7087e-07 | 4.4817 | 3.0956e-07 | 0.22313 | 0.125 | 3: 9.8676e-09; Number of servers 1: 1.5; Number of servers 2: 3.2892e-10; Number of servers 3: 0.05
13 | 3.1254e-08 | 4.4817 | 3.5331e-08 | 0.22313 | 0.11538 | 3: 1.0283e-09; Number of servers 1: 1.5; Number of servers 2: 3.4275e-11; Number of servers 3: 0.05
14 | 3.3486e-09 | 4.4817 | 3.7505e-09 | 0.22313 | 0.10714 | 3: 1.0042e-10; Number of servers 1: 1.5; Number of servers 2: 3.3474e-12; Number of servers 3: 0.05
15 | 3.3486e-10 | 4.4817 | 3.7207e-10 | 0.22313 | 0.1 | 3: 9.2245e-12; Number of servers 1: 1.5; Number of servers 2: 3.0748e-13; Number of servers 3: 0.05
16 | 3.1394e-11 | 4.4817 | 3.4641e-11 | 0.22313 | 0.09375 | 3: 7.996e-13; Number of servers 1: 1.5; Number of servers 2: 2.6653e-14; Number of servers 3: 0.05
17 | 2.77e-12 | 4.4817 | 3.0381e-12 | 0.22313 | 0.088235 | 3: 6.5602e-14; Number of servers 1: 1.5; Number of servers 2: 2.1867e-15; Number of servers 3: 0.05
18 | 2.3083e-13 | 4.4817 | 2.5182e-13 | 0.22313 | 0.083333 | 3: 5.1081e-15; Number of servers 1: 1.5; Number of servers 2: 1.7027e-16; Number of servers 3: 0.05
19 | 1.8224e-14 | 4.4817 | 1.9786e-14 | 0.22313 | 0.078947 | 3: 3.7841e-16; Number of servers 1: 1.5; Number of servers 2: 1.2614e-17; Number of servers 3: 0.05
20 | 1.3668e-15 | 4.4817 | 1.4776e-15 | 0.22313 | 0.075 | 3: 2.6732e-17; Number of servers 1: 1.5; Number of servers 2: 8.9108e-19; Number of servers 3: 0.05
21 | 9.7628e-17 | 4.4817 | 1.0514e-16 | 0.22313 | 0.071429 | 3: 1.8046e-18; Number of servers 1: 1.5; Number of servers 2: 6.0152e-20; Number of servers 3: 0.05
22 | 6.6564e-18 | 4.4817 | 7.1435e-18 | 0.22313 | 0.068182 | 3: 1.1663e-19; Number of servers 1: 1.5; Number of servers 2: 3.8876e-21; Number of servers 3: 0.05
23
24
25
26
27
28
29
30
Note on A1: Created by Excel OM/QM version 5.2.116
Note on A4: Waiting Lines: Submodel = 0; Problem size @ 2 by 2
The arrival RATE and service RATE both must be rates and use the same time unit. Given a time such as 10 minutes, convert it to a rate such as 6 per hour.