TO: President, BlueNote Inc.

FROM: Ricardo Smith

Date: March 13, 2021

RE: GAA Fishing Expedition

Risk

There are numerous risks that Great Alaska Adventures (GAA) is bound to experience with during the fishing expedition. GAA needs to identify the potential risks and come up with contingency plans to prevent the risks from happening. Risks can occur during the start of a trip while others can occur in the middle of the trip. It is imperative for GAA to plan for these risks and overcome them before they bring devastating consequences. To overcome such risks, GAA has to be proactive in putting measures that mitigate the risks.

Some of the possible risks associated with this project include bad weather conditions, medical emergencies, plane problems, lost equipment, accidents, problems with licenses and communication problems. Weather conditions such as heavy rainfall and cloudiness make travel by air a problem and may pose a great risk when travelling because it inhibits visibility. Plane problems is another inevitable problem that is caused by the shortcomings of technology. Planes can develop problems before take-off or even in the air. Accidents is another potential risk that can cause problems during the expedition.

FIGURE 7.6: Risk Assessment form

| Risk Event | Likelihood | Impact | Detection Difficulty | When |
| --- | --- | --- | --- | --- |
| Plane problems to and from base camps | 5 | 5 | 2 | To and from base camps |
| Weather problems | 4 | 3 | 2 | Before and during the fishing trip |
| Licensing problems | 3 | 5 | 1 | During trip |
| Accidents | 6 | 7 | 8 | During trip |
| Lost Equipment | 2 | 3 | 2 | During trip |
| Communication | 3 | 2 | 2 | During trip |

Note: The rating in this table is out of 10

Figure 7.8 Risk Response matrix

| Risk Response Matrix |  |  |  |  |
| --- | --- | --- | --- | --- |
| Risk Event | Response | Contingency Plan | Trigger | Who is Responsible |
| Weather problems | Consult the nearest weather station | Have alternative means of transport | Depending on severity of weather | Great Alaska Adventures |
| Plane problems to and from base camps | Have standby engineers to check any problems | Have more than 2 planes | Soon as time delay is established | Great Alaska Adventures |
| Communication problems | Have backup at base camps | Have backup equipment | Once equipment breaks use backup | Great Alaska Adventures |
| Licensing problems | Have proper training for staff | Ensure all staff especially pilots have licenses | Federal Aviation Administration | Great Alaska Adventures |
| Accident | Have staff training for health emergencies | Have emergency evacuation plan ready | depending on severity of problem | Great Alaska Adventures/BlueNote |
| Lost Equipment | Have backup equipment | Have more equipment sent | After the loss of an equipment | Great Alaska Adventures/BlueNote |