## Slide 1: Project Kickoff
Customer Service Phone App

## Slide 2: Goals and Objectives
Provide convenient/on-the-go customer service
  Phone app will allow customer to:
    Schedule service call
    Online chat with service agent
    Leave text message
    Get customer status

## Slide 3: Project Scope
In Scope:
  Support for Android and iOS
  Features:
    Chat
    Text
    Customer status
Out of Scope:
  Support for Windows and Blackberry
  Features:
    Integration with website (future)
Notes: May require more than one slide

## Slide 4: Budget / Sponsor
Approximate Cost – $200,000
Sponsor – Customer Service Area

## Slide 5: Implementation Timeline
Design – week of 5/7/18
  Features
    User Stories
      Scenarios
      Acceptance Criteria/Conditions of Satisfaction
Sprints – 6 weeks (5/14 – 6/22)
  UX
  Back end
  Reporting
UAT – User Acceptance – 2 weeks ( 6/25 – 7/13)
Release – 2 weeks (7/16 -7/27)
Notes: May require more than one slide

## Slide 6: Risk Factors
Availability of resources:
  PM assigned to multiple projects
  Product owner availability (still has “day job”)
  Developers still have to support existing apps
New technology
  Chat feature
  Text interface

## Slide 7: Project Team Roles and Responsibilities
[Full Name] Project Manager
[Full Name] Product Owner
[Full Name] Developer UX
[Full Name] Developer DB/API
[Full Name] Developer Reporting
[Full Name] Tester QA/UAT

## Slide 8: Team/Stakeholder Communications
Team meetings
Status reports
E-mail updates
Shared project folder