QUESTION 1

Precedence Diagram

I

I

C              C

C              C

K

K

J

J

G

G

H

H

E

E

F

F

D

D

B

B

A             A

A             A

| ACTIVITY | ES | EF | LS | LF | DURATION | SLACK |
| --- | --- | --- | --- | --- | --- | --- |
| A | 0 | 1 | 0 | 1 | 1 | 0 |
| B | 1 | 3 | 8 | 10 | 2 | 7 |
| C | 1 | 7 | 1 | 7 | 6 | 0 |
| D | 7 | 12 | 10 | 15 | 5 | 3 |
| E | 7 | 16 | 7 | 16 | 9 | 0 |
| F | 7 | 8 | 22 | 23 | 1 | 15 |
| G | 12 | 16 | 15 | 19 | 4 | 3 |
| H | 16 | 19 | 23 | 26 | 3 | 7 |
| I | 16 | 19 | 16 | 19 | 3 | 0 |
| J | 19 | 26 | 19 | 26 | 7 | 0 |
| K | 26 | 28 | 26 | 28 | 2 | 0 |

POSSIBLE PATHS

Path 1; A	B	D	G	J	K      Duration: 21 days Slack: 13 days

Path 2: A	C	E	I	J	K      Duration: 28days Slack: 0 days

Path 3; A	C	E	H	K            Duration: 21 days Slack: 7 days

Path 4; A	C	F	H	K           Duration: 13 days Slack: 7 days

Path 5; A	C	D	G	J	K       Duration: 25 days Slack: 6 days

CRITICAL PATH

A	C	E	I	J	K Duration: 28 days Slack: 0 days

QUESTION 2

If activity F is delayed by a week, it won't impact the total project duration. This is because Activity F is not on the critical path, and any delay made on an activity not on the critical path does not affect the project's end date as long as the total float or slack isn't surpassed. In this case, the activity's F slack is 15 days; therefore, a delay of 7 days won't affect the total project duration.