## Sheet1
WBS NUMBER | LEVEL 0 | LEVEL 1 | LEVEL 2 | LEVEL 3
Tunnel Construction
1 |  | Site Delivery
1.1 |  |  | Survey
1.1.1 |  |  |  | Investigate subsurface
1.1.2 |  |  |  | Report on Geotechnics
1.1.3 |  |  |  | Ground behaviour, management
1.1.4 |  |  |  | Impacts on the third party
1.1.5 |  |  |  | Investigating the unique harzards
1.2 |  |  | Initial Design
1.2.1 |  |  |  | Project configuration
1.2.2 |  |  |  | Excavation plan
1.2.3 |  |  |  | Selecting construction method
1.2.4 |  |  |  | Engineering and mapping
1.3 |  |  | Comprehensive Design
1.3.1 |  |  |  | Route finalization
1.3.2 |  |  |  | Concluding feasibility
1.3.3 |  |  |  | Pre-architectural engineering
1.3.4
2 |  | Approving drawings
2.1 |  |  | Documents
2.1.1 |  |  |  | Memo of design
2.1.2 |  |  |  | Charters of construction
2.1.3 |  |  |  | Engineering appraial
2.1.4 |  |  |  | Specifications
2.2 |  |  | Collective consent
2.2.1 |  |  |  | Review of envoronmental notices
2.2.2 |  |  |  | Collective comment
2.2.3 |  |  |  | Interview
2.3 |  |  | Mandating
2.3.1 |  |  |  | Bid collection
2.3.2 |  |  |  | Sessions of project information
2.3.3 |  |  |  | Reviewing and selection of bids
3 |  | Convention
3.1 |  |  | Procurement
3.1.1 |  |  |  | The bill of quantities
3.1.2 |  |  |  | Equipment
3.1.3 |  |  |  | Machinery of boring the tunnel
3.2 |  |  | Elements of fabricate structur
3.2.1 |  |  |  | Building the emitting channel
3.2.2 |  |  |  | Discharge lining partitions
3.2.3 |  |  |  | Segments of float lining
3.3 |  |  | Preparing the site
3.3.1 |  |  |  | Relocating utility
3.3.2 |  |  |  | Staging space
3.3.3 |  |  |  | Ventilating the site
3.3.4 |  |  |  | Backup system
4 |  | Construction
4.1 |  |  | Unearthing
4.1.1 |  |  |  | Drilling
4.1.2 |  |  |  | Tunnel hiking
4.1.3 |  |  |  | Jet grouting
4.1.4 |  |  |  | Earth freezing
4.1.5 |  |  |  | Cross pathways
4.2 |  |  | Base
4.2.1 |  |  |  | Installing pile
4.2.2 |  |  |  | Pillar collumns
4.2.3 |  |  |  | Short term lining
4.2.1 |  |  |  | Cofferdam
4.3 |  |  | Lining
4.3.1 |  |  |  | Staging lining segments
4.3.2 |  |  |  | Lining installation
4.3.3 |  |  |  | Sub-program
5 |  | Closure
5.1 |  |  | Try out
5.1.1 |  |  |  | Testing the systems of life-safety
5.1.2 |  |  |  | Aunthetication
5.2 |  |  | Training
5.2.1 |  |  |  | Operators worrkshop and training
5.2.2 |  |  |  | Training the operations ofemergence coordination
5.3 |  |  | Demobilising
5.3.1 |  |  |  | Staging site decommisioning
5.3.2 |  |  |  | Removing machinery
5.3.3 |  |  |  | The last paving