## Work Breakdown Structure
Work Breakdown Structure
Project Name: |  | House construction
Task # | Task Name | Duration | Start | Finish | Predecessors | Resource Names
1 | DESIGNING AND PERMITS | 7days | 1st june | 8th june |  | permits and drawings
1.1.1 | identyfing the type of house desing | 1 day | 1st june | 2nd |  | consultation
1.1.2 | searching for a qualified architec to desing | 1 day | 2nd | 3rd june | consultation | labor and money
1.1.3 | the design work starts | 1 day | 3rd june | 4th june | architect | desinging softwares
1.1.4 | completion of the design | 2days | 4th | 6th june | architect | desinging softwares
1.1.5 | searching for permits | 2 days | 6th | 8th june | design | labor and money
2 | PROCUREMENT | 5 days | 10th june | 2020-06-15 | permits | money
2.2.1 | procurement of bricks | 6days | 10th june | 11th june | permits | bricks
2.2.3 | procurement of cement and sand | 1day | 11th | 11th june | bricks | cement, sand
2.2.4 | procurement of ironsteel | 1 day | 12th | 12th june | cement and sand | ironsteel
2.2.5 | procurement of roofing materials | 1day | 13th | 13th june | ironsteel | ironsheets and nails
2.2.6 | procurement of electrical and plumbing materials | 1day | 14th | 14th june | ironsheets | wires, bulbs, switchs,
2.2.7 | procurement finishing materials | 1day | 15th | 15th june | electricals | paint
3 | CONSTRUCTION | 67 days | 18th june | 6th of september | procument | labor
3.3.1 | common temporary work | 2days | 18th | 20th june | tools | labor
3.3.2 | temporary work | 2 days | 21st june | 23rd june | tools | labor
3.3.3 | earth and foundation construction | 7 days | 24th june | 2rd july | tools and materials | labor
3.3.4 | reinforced concrete work | 7 days | 3rd july | 1oth july | tools and materials | labor
3.3.5 | masonry work | 7 days | 11th july | 18th july | tools and materials | labor
3.3.6 | plaster work | 7 days | 19th july | 26th july | tools and materials | labor
3.3.7 | furniture and capentry works | 7 days | 27th july | 5thy august | tools and materials | labor
3.3.8 | waterproof work | 7 days | 6th august | 13th august | tools and materials | labor
3.3.9 | tile work | 7 days | 14th august | 21st august | tools and materials | labor
3.3.10 | window work | 7 days | 22rd auigust | 29th august | tools and materials | labor
3.3.11 | glass work | 7 days | 30th august | 6th september | tools and materials | labor
4 | INSPECTION | 3 days | 7th september | 10th september | construction completed | labor
4.4.1 | inspection of interior work | 1 day | 7th september | 8th september | inspector of interial works | labor
4.4.2 | inspection of the exterior | 1 day | 8th september | 9th september | inspector of exterior work | labor
4.4.3 | inpection of plumbing and electrical work | 1 day | 9th september | 10th september | electrician and a plumber | labor
5 | TURNOVER | 1 day | 11th september | 11th septwmber | all the work completed | labor