DayJa Lowe

Columbia Southern University

April 17, 2020

# Current state analysis (CSA

## Complete an inventory of all physical and virtual servers.

## Complete an inventory of all software applications currently being provided, and assign a critical index factor (CIF) for each.

## Identify what an acceptable downtime would be for each application.

### Determine the interdependencies between applications, servers, storage, and telecommunications.

### Conduct a benchmarking of existing performance metrics of data center operations.

### Determine viability of moving existing equipment or cost-benefit of procuring new equipment.

# Planning and management

## Identify potential costs.

## Develop a budget.

## Develop a process list of all anticipated move-related tasks.

## Determine lessons learned from past moves.

## Test move processes to identify problems or issues.

## Obtain stakeholder approval to continue project.

# Data center move strategy

## Identify key personnel who will be involved with executing the move.

### Determine if outsourcing of tasks is required.

## Identify potential risks.

### Develop risk mitigation processes.

## Assign servers and applications to move bundles.

## Prioritize the order in which bundles will be moved to the new data center.

# Data center migration

## Shift data center operations to a back-up site.

## Verify operations are working properly.

## Shut down current operations.

## Procure/order new equipment required.

## Uninstall existing equipment.

## Prepare for shipment.

## Track shipment.

## Receive shipments at new data center.

### New procurements

### Existing equipment

## Install equipment.

### Test and verify.

## Install software/applications.

### Test and verify.

## Migrate live data from backup site.

### Test and verify.

# Post-move verification

## Ensure all installations are complete.

## Conduct post-move benchmarks of performance, and compare with pre-move

## Benchmarks to determine delta (difference), if any.

## Obtain stakeholder approval and acceptance.