ID

1

Task

Mode

Task Name

Duration Mar 3, '19Start

W

T

F

S

Mar 10, '19

SM

T

W

T

F

S

Mar 17, '19

SM

1.0 Upgrade OMOP common 38 days?

data model software

1.1 Requirement

gathering

1.1.1 Site Survey

1.1.2 Create office

groupings

1.1.3 Analysis report

1.2 Selection and Design

1.2.1 Purchase

computers

1.2.2 Purchase software

1.2.3 Purchase Cabling

Accessories

1.3 Implementation

1.3.1 Back-up shared

Drives

1.3.2 Back-up Local user

drives

1.4 Installation, operation

and configuration

1.4.1 Set-up Network

1.4.1.1 Run Cables

Task

Split

Thu 3/7/19

2

3

4

5

6

7

8

9

10

11

12

13

5 days

2 days

2 days

1 day

7 days

3 days

2 days

2 days

4 days

3 days

1 day?

1 day?

Thu 3/7/19

Thu 3/7/19

Mon 3/11/19

Wed 3/13/19

Fri 3/15/19

Fri 3/15/19

Wed 3/20/19

Fri 3/22/19

Fri 3/29/19

Fri 3/29/19

Mon 4/1/19

Tue 4/2/19

14

15

2 days

2 days

Tue 4/2/19

Tue 4/2/19

External Milestone

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Page 1

Manual Summary Rollup

Manual Summary

Start-only

Finish-only

Deadline

Progress

Project: WBS

Date: Thu 3/7/19

Milestone

Summary

Project Summary

External Tasks

ID

16

17

18

19

Task

Mode

Task Name

Duration Mar 3, '19Start

W

T

F

S

Mar 10, '19

SM

T

W

T

F

S

Mar 17, '19

SM

20

21

22

23

24

25

26

27

28

29

1.4.1.2 Set-up2 days

Routers

1.4.1.2.1 Configure 2 days

Firewall

1.4.1.2.2 Set-up static 2 days

ip's

1.4.1.2.3 Create2 days

passwords and access

rules

1.4.2 Set-up Users1 day?

1.4.2.1 Set-up2 days

computer

1.4.2.2 Install2 days

software

1.4.2.3 Configure2 days

settings for network

1.4.2.4 Configure2 days

Printer

1.4.2.5 Restore Data 2 days

1.5 Train Staff1 day?

1.5.1 Create user2 days

reference materials

1.5.2 Facilitate Lunch and 2 days

learns

1.5.3 Deliver one on one 2 days

trouble shooting

Task

Split

Thu 4/4/19

Mon 4/8/19

Wed 4/10/19

Fri 4/12/19

Tue 4/16/19

Tue 4/16/19

Thu 4/18/19

Mon 4/22/19

Wed 4/24/19

Fri 4/26/19

Tue 4/30/19

Tue 4/30/19

Thu 5/2/19

Mon 5/6/19

External Milestone

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Page 2

Manual Summary Rollup

Manual Summary

Start-only

Finish-only

Deadline

Progress

Project: WBS

Date: Thu 3/7/19

Milestone

Summary

Project Summary

External Tasks

Mar 17, '19

M

T

W

T

F

S

Mar 24, '19

SM

T

W

T

F

S

Mar 31, '19

SM

T

W

T

F

S

Apr 7, '19

SM

T

W

T

F

Task

Split

Project: WBS

Date: Thu 3/7/19

Milestone

Summary

Project Summary

External Tasks

External Milestone

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Page 3

Manual Summary Rollup

Manual Summary

Start-only

Finish-only

Deadline

Progress

Mar 17, '19

M

T

W

T

F

S

Mar 24, '19

SM

T

W

T

F

S

Mar 31, '19

SM

T

W

T

F

S

Apr 7, '19

SM

T

W

T

F

Task

Split

Project: WBS

Date: Thu 3/7/19

Milestone

Summary

Project Summary

External Tasks

External Milestone

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Page 4

Manual Summary Rollup

Manual Summary

Start-only

Finish-only

Deadline

Progress

S

Apr 14, '19

SM

T

W

T

F

S

Apr 21, '19

SM

T

W

T

F

S

Apr 28, '19

SM

T

W

T

F

S

May 5, '19

SM

T

W

Task

Split

Project: WBS

Date: Thu 3/7/19

Milestone

Summary

Project Summary

External Tasks

External Milestone

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Page 5

Manual Summary Rollup

Manual Summary

Start-only

Finish-only

Deadline

Progress

S

Apr 14, '19

SM

T

W

T

F

S

Apr 21, '19

SM

T

W

T

F

S

Apr 28, '19

SM

T

W

T

F

S

May 5, '19

SM

T

W

Task

Split

Project: WBS

Date: Thu 3/7/19

Milestone

Summary

Project Summary

External Tasks

External Milestone

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Page 6

Manual Summary Rollup

Manual Summary

Start-only

Finish-only

Deadline

Progress