Week Two Assignment: Part 2

Name

Institution

Week Two Assignment: Part 2

- Job fair’s list of activities

| Task # | Task Description | Estimated Number of Days |
| --- | --- | --- |
| TASK One | Preparation of the checklist for the job fair which covers core components |  |
|  | List preparation | 5 |
|  | Set up a meeting with the people in charge | 4 |
|  | Confirm the list | 4 |
| Task Two | Confirm the date, time and place for the job fair |  |
|  | Confirmation of event Time and date | 4 |
|  | Identify the venue size | 4 |
|  | Locating the venue. | 6 |
| Task Three | Prepare the job fair budget |  |
|  | Make a list of all the required equipment | 3 |
|  | Estimate the cost for paper suppliers, refrigerators ,and furniture | 3 |
|  | Confirmation of the list | 3 |
| Task Four | Advertising the job fair |  |
|  | Create the advertising plan | 3 |
|  | create and post flyers in your area | 4 |
|  | Invite the potential exhibitors through a letter | 4 |
|  | Promote the job fair on various social media platforms (Twitter, Facebook, etc.) | 2 |
|  | Post it in the newspaper. | 4 |
| Task Five | Contact local companies, corporations organizing for the tables setups |  |
|  | Create the list of organizations in the regions | 3 |
|  | Find the addresses and other contact information for the HR directors for every business organization, and contact them | 4 |
| Task Six | Organizing the printing of the résumé book |  |
|  | Ask the learners to hand in the updated résumés | 40 |
|  | Set the deadline for the submission of the resumes | 2 |
|  | Organize as well print the resumes at the submission day | 3 |
| Task Seven | Print signs and symbols for the job fair to direct the potential exhibitors as well as job seekers |  |
|  | Organize and print the direction signs | 4 |
|  | Put the signs in the strategic areas | 3 |
| Task Eight | Receive the feedback from the attendees of job fair |  |
|  | Create the survey form | 2 |
|  | Give the job seekers the survey forms as they enter | 1 |
|  | collect the survey forms | 1 |

- Create a work breakdown structure

- Gantt chart proposal