## Sheet1
Name | Duration |  |  | Tools | Resources
E-Library Management System | 30 days | 2019-01-01 | 2019-01-30
Project set-up | 5 days | 2019-01-01 | 2019-01-05
Problem decription | 1 day | 2019-01-01 | 2019-01-01 |  | Project Manager
Establishing main objective | 1 day | 2019-01-01 | 2019-01-02 |  | Lead Administrator
Setting up operation environment | 1 day | 2019-01-02 | 2019-01-03 |  | Lead Administrator
Identifying system requirements | 2 days | 2019-01-03 | 2019-01-05 |  | Lead Developer
Project set-up complete | 0 days | 2019-01-05 | 2019-01-05
Module 1 | 6 days | 2019-01-05 | 2019-01-11
Teacher Module | 0 days | 1/5/2019 1/5/2019
Draft UML diagram | 2days | 1/5/2019 1/7/2019 |  |  | Lead Developer
Draft database model | 2days | 1/7/2019 1/9/2019 |  | SQL | SQL Developer
Launch Java IDE and start project | 2 days | 1/9/2019 1/11/2019 |  | PHP | PHP Developer
Model 1 complete | 0 days | 1/11/2019 1/11/2019 |  | MySQL | MYSQL Developer
Module 2 | 6 days | 1/11/2019 1/17/2019
User Interface (UI) | 0 days | 1/11/2019 1/11/2019
Create layers within Java Resources | 3 days | 1/11/2019 1/14/2019 |  | JAVA | Java Developer
Create iBatis sq Imap | 3 days | 1/14/2019 1/17/2019 |  |  | Lead Developer
Module 2 complete | 0 days | 1/17/2019 1/17/2019 |  |  | Lead Developer
Module 3 | 7 days | 2019-01-17 | 2019-01-24
Web pages | 0 days | 2019-01-17 | 2019-01-17 | HTML | HTML Developer
Implement JSP | 2 days | 2019-01-17 | 2019-01-19 |  | Lead Developer
Create forms using Spring framework | 2 days | 2019-01-19 | 2019-01-21 | JavaScript | Javascript Developer
Implement Dojo Toolkit | 3 days | 2019-01-21 | 2019-01-24 |  | Lead Developer
Module 3 complete | 0 days | 2019-01-24 | 2019-01-24
Module 4 | 6 days | 2019-01-24 | 2019-01-30
Layer Intercommunication | 0 days | 2019-01-24 | 2019-01-24 | CSS | CSS Developer
Create DB and JSP pages | 2 days | 2019-01-24 | 2019-01-26 |  | Lead Developer
Test session for security | 1 day | 2019-01-26 | 2019-01-27 |  | Test Engineer
Test login for security | 1 day | 2019-01-26 | 2019-01-27 |  | Test Engineer
Implement Jquery | 3 days | 2019-01-30 | 2019-01-30 |  | Lead Developer
Model 4 complete | 0 days | 2019-01-30 | 2019-01-30
Project Completed | 0 days | 2019-01-30 | 2019-01-30