## Sheet2
Task | Start Date | Days to Complete | Budget
Wedding Project |  |  | $20,000
Establishment of the Wedding Date | 2021-08-18 | 1 | $600
Acquistion of the Marriage License | 2021-08-24 | 6 | $1000
Preparations for the Ceremony | 2021-08-29 | 5 | $3000
Establishing the Rent for the Church | 2021-09-03 | 5 | $1400
Hiring the Florist | 2021-09-12 | 9 | $1400
Creating the Wedding Program | 2021-09-21 | 9 | $200
Hiring a photographer and videographer | 2021-10-05 | 14 | $2000
Wedding Ceremony
Guest activities and Details | 2021-10-25 | 20 | $200
Creating a Guest List | 2021-11-01 | 7 | $200
Sorting Invitations | 2021-11-16 | 15 | $200
Sending Wedding Invitations | 2021-11-24 | 8 | $400
Tracking RSVPs
Preparation for Reception | 2021-12-05 | 11 | $1200
Reserving a Reception Hall | 2021-12-28 | 23 | $1400
Food and Beverage
Choosing a Caterer | 2022-01-05 | 8 | $1200
Creating a Menu | 2022-01-12 | 7 | $2000
Making Final Orders | 2022-01-18 | 6 | $400
Hiring Entertainment | 2022-01-23 | 5 | $2200
Decorating the Reception Hall | 2022-01-26 | 3 | $1000
Wedding Reception | 2022-01-28 | 1 | $3000