## Resource & Cost
WBS | Task Name | Labor | Hours | Rate | Labor Total | Supplies | Quantity | Price | Supplies Total | Total | Notes
1 | MMBSS Customer Relations System
1.1 | Project Initiation Phase
1.1.1 | Project Team
1.1.1.1 | Identify Project Team Members and Establish Project Team | Project Manager | 8 | 65 | 520 |  |  |  |  | 520
1.1.1.2 | Finalize Project Team Members | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.1.2 | Project Kickoff |  |  |  | 0 |  |  |  |  | 0
1.1.2.1 | Schedule Kickoff Meeting | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.1.2.2 | Prepare Draft Project Agenda | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.1.2.3 | Prepare Draft Kickoff Presentation | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.1.2.4 | Review and Finalize Project Agenda and Kickoff Presentation | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.1.2.5 | Deliver Project Kickoff Materials to Project Sponsor | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.1.2.6 | Conduct Project Kickoff Meeting | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
|  | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
|  | Control Manager | 4 | 45 | 180 |  |  |  |  | 180
|  | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
1.2 | Project Management Phase |  |  |  | 0 |  |  |  |  | 0
1.2.1 | Project Scope |  |  |  | 0 |  |  |  |  | 0
1.2.1.1 | Analyze and Draft Project Scope | Project Manager | 18 | 65 | 1170 |  |  |  |  | 1170
1.2.1.2 | Review Project Scope with Project Sponsor | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.2.1.3 | Update Project Scope based on Feedback | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.2.1.4 | Review Finalized Project Scope with Project Sponsor | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.2.1.5 | Obtain Project Sponsor Approval for Project Scope | Project Manager | 0 | 65 | 0 |  |  |  |  | 0
1.2.2 | Project Plan |  |  |  | 0 |  |  |  |  | 0
1.2.2.1 | Review and Update Project Plan | Project Manager | 16 | 65 | 1040 |  |  |  |  | 1040
|  | Technical Lead | 16 | 55 | 880 |  |  |  |  | 880
|  | Web Developer | 16 | 50 | 800 |  |  |  |  | 800
|  | Control Manager | 16 | 45 | 720 |  |  |  |  | 720
|  | Implementation Lead | 16 | 55 | 880 |  |  |  |  | 880
1.2.2.2 | Deliver Updated Project Plan to Project Sponsor | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.2.2.3 | Obtain and Incorporate Feedback from Project Sponsor | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
|  | Control Manager | 4 | 45 | 180 |  |  |  |  | 180
|  | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.2.2.4 | Review Project Plan with Project Sponsor | Project Manager | 1 | 65 | 65 |  |  |  |  | 65
1.2.2.5 | Obtain Project Sponsor Approval and Sign-Off | Project Sponsor | 0 | 0 | 0 |  |  |  |  | 0
1.2.3 | Project Meetings |  |  |  | 0 |  |  |  |  | 0
1.2.3.1 | Weekly Status Meetings | Project Manager | 26 | 65 | 1690 |  |  |  |  | 1690
|  | Technical Lead | 26 | 55 | 1430 |  |  |  |  | 1430
|  | Web Developer | 26 | 50 | 1300 |  |  |  |  | 1300
|  | Control Manager | 26 | 45 | 1170 |  |  |  |  | 1170
|  | Implementation Lead | 26 | 55 | 1430 |  |  |  |  | 1430
1.2.3.2 | Monthly Status Meetings | Project Manager | 8 | 55 | 440 |  |  |  |  | 440
1.3 | Project Requirements Phase |  |  |  | 0 |  |  |  |  | 0
1.3.1 | Business Requirements |  |  |  | 0 |  |  |  |  | 0
1.3.1.1 | Schedule Business Requirements Sessions with Project Sponsor | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.3.1.2 | Extract and Review Business Requirements from Project Charter | Project Manager | 8 | 65 | 520 |  |  |  |  | 520
1.3.1.3 | Conduct Initial Business Requirements Session with Stakeholders | Project Manager | 8 | 65 | 520 |  |  |  |  | 520
1.3.1.4 | Update Business Requirements based on Feedback Received | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.3.1.5 | Review Business Requirements Updates with Project Sponsor | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.3.1.6 | Conduct Follow-up Business Requirements Session with Stakeholders | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
1.3.1.7 | Review and Finalize Business Requirements with Project Sponsor | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.3.1.8 | Obtain Business Requirements Sign-Off from Project Sponsor | Project Manager | 0 | 65 | 0 | Xerox Work Centre 3335/DNI All-In-One Laser printer | 1 | 350 |  | 0
1.3.2 | System Requirements |  |  |  | 0 |  |  |  |  | 0
1.3.2.1 | SysPro ERP |  |  |  | 0 |  |  |  |  | 0
1.3.2.1.1 | Identify SysPro ERP Requirements (hardware, software, licenses, etc.) | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
1.3.2.1.2 | Review and Finalize SysPro ERP Requirements | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.3.2.1.3 | Submit SysPro ERP Purchase Order for Approval | Project Manager | 0 | 65 | 0 | SysPro ERP System | 1 | 1500 | 1500 | 1500
1.3.2.1.4 | Obtain Purchase Order Approval for SysPro ERP | Project Manager | 0 | 65 | 0 |  |  |  |  | 0
1.3.2.1.5 | Submit Purchase Order to SysPro | Technical Lead | 2 | 55 | 110 |  |  |  |  | 110
1.3.2.2 | Clover POS |  |  |  | 0 |  |  |  |  | 0
1.3.2.2.1 | Identify Clover POS Requirements (hardware, software, licenses, etc.) | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.3.2.2.2 | Review and Finalize Clover POS Requirements | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
|  | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
1.3.2.2.3 | Submit Clover POS Purchase Order for Approval | Project Manager | 0 | 65 | 0 | Clover POS System | 1 | 1200 | 1200 | 1200
1.3.2.2.4 | Obtain Purchase Order Approval for Clover POS | Projcet Manager | 0 | 0 | 0 |  |  |  |  | 0
1.3.2.2.5 | Submit Purchase Order to Clover | Technical Lead | 2 | 55 | 110 |  |  |  |  | 110
1.3.2.3 | Custom Website |  |  |  | 0 |  |  |  |  | 0
1.3.2.3.1 | Identify Custom Website Requirements (hardware, software, domain registration, etc.) | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
|  | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
1.3.2.3.2 | Review and Finalize Custom Website Requirements | Project Manager | 2 | 65 | 130 |  |  |  |  | 130
|  | Technical Lead | 2 | 55 | 110 |  |  |  |  | 110
|  | Implementation Lead | 2 | 55 | 110 |  |  |  |  | 110
|  | Web Developer | 2 | 50 | 100 |  |  |  |  | 100
1.3.2.3.3 | Obtain Purchase Order Approval to Purchase Custom Website Infrastructure | Project Manager | 0 | 65 | 0 |  |  |  |  | 0
1.3.2.3.4 | Submit Purchase Order to Support Cloud Infrastructure | Technical Lead | 1 | 55 | 55 |  |  |  |  | 55
1.3.2.3.5 | Submit Purchase Order to Domain Provider | Technical Lead | 1 | 55 | 55 |  |  |  |  | 55
1.3.3 | Vendor Agreements |  |  |  | 0 |  |  |  |  | 0
1.3.3.1 | Obtain Service Agreement with ISP (FIOS) | Technical Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.3.2 | Obtain End-User Agreements from SysPro ERP | Technical Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.3.3 | Obtain End-User Agreements from Clover POS | Technical Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.3.4 | Obtain Cloud Infrastructure Agreement | Technical Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.3.5 | Obtain End-User Agreement with Domain Provider | Technical Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.3.6 | Review End-User and Service Agreements with Project Sponsor | Project Manager | 8 | 65 | 520 |  |  |  |  | 520
1.3.3.7 | Obtain End-User and Service Agreements Sign-Offs | Project Sponsor | 0 | 0 | 0 |  |  |  |  | 0
1.3.4 | Network Infrastructure |  |  |  | 0 |  |  |  |  | 0
1.3.4.1 | Identify Network Requirements including routers, firewall, etc. | Technical Lead | 16 | 55 | 880 |  |  |  |  | 880
|  | Implementation Lead | 16 | 55 | 880 |  |  |  |  | 880
|  | Project Manager | 16 | 65 | 1040 |  |  |  |  | 1040
1.3.4.2 | Review Network Requirements with Project Sponsor | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Project Manager | 4 | 65 | 260 | Dell Vostro 15” Small Business Laptops | 2 | 1000 | 2000 | 2260
[5 empty] | 0 | Sophos XG 135 Wireless Next Gen Firewall | 1 | 1531 | 1531 | 1531
[6 empty] | 1,000 feet of Cat 6A cable | 1000 | 1.6 | 1600 | 1600
1.3.4.3 | Obtain Project Sponsor Approval for Network Infrastructure | Project Manager | 0 | 65 | 0 |  |  |  |  | 0
1.3.4.4 | Initiate and Submit Purchase Order for Network Infrastructure | Technical Lead | 4 | 55 | 220 |  |  |  |  | 220
1.3.5 | Obtain Hardware |  |  |  | 0 |  |  |  |  | 0
1.3.5.1 | Receive SysPro ERP components | Implementation Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.5.2 | Receive Clover POS components | Implementation Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.5.3 | Receive Hardware to Support Website Installation | Implementation Lead | 0 | 55 | 0 |  |  |  |  | 0
1.3.5.4 | Receive Network Infrastructure Hardware | Implementation Lead | 0 | 55 | 0 |  |  |  |  | 0
1.4 | Project Development Phase |  |  |  | 0 |  |  |  |  | 0
1.4.1 | Development Iteration 1 |  |  |  | 0 |  |  |  |  | 0
1.4.1.1 | Finalize Work Package 1 | Project Manager | 8 | 65 | 520 |  |  |  |  | 520
|  | Implementation Lead | 8 | 55 | 440 |  |  |  |  | 440
|  | Web Developer | 8 | 50 | 400 |  |  |  |  | 400
1.4.1.2 | Develop, Test and Debug Work Package 1 | Web Developer | 76 | 50 | 3800 |  |  |  |  | 3800
|  | Web Developer Consultant | 76 | 50 | 3800 |  |  |  |  | 3800
1.4.1.3 | Initial demo of Custom Website | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
1.4.1.4 | Additional Development based on feedback on Work Package 1 | Web Developer | 24 | 50 | 1200 |  |  |  |  | 1200
1.4.2 | Development Iteration 2 |  |  |  | 0 |  |  |  |  | 0
1.4.2.1 | Finalize Work Package 2 | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
|  | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
1.4.2.2 | Develop, Test and Debug Work Package 2 | Web Developer | 84 | 50 | 4200 |  |  |  |  | 4200
|  | Web Developer Consultant | 84 | 50 | 4200 |  |  |  |  | 4200
1.4.2.3 | Additional Development based on feedback on Work Package 2 | Web Developer | 16 | 50 | 800 |  |  |  |  | 800
|  | Web Developer Consultant | 16 | 50 | 800 |  |  |  |  | 800
1.4.3 | Development Iteration 3 |  |  |  | 0 |  |  |  |  | 0
1.4.3.1 | Finalize Work Package 3 | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
|  | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
1.4.3.2 | Develop, Test and Debug Work Package 3 | Web Developer | 72 | 50 | 3600 |  |  |  |  | 3600
|  | Web Developer Consultant | 72 | 50 | 3600 |  |  |  |  | 3600
1.4.3.3 | Additional Development based on feedback on Work Package 3 | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
|  | Web Developer Consultant | 4 | 50 | 200 |  |  |  |  | 200
1.4.4 | Development Iteration 4 |  |  |  | 0 |  |  |  |  | 0
1.4.4.1 | Finalize Work Package 4 | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
|  | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
1.4.4.2 | Develop, Test and Debug Work Package 4 | Web Developer | 72 | 50 | 3600 |  |  |  |  | 3600
|  | Web Developer Consultant | 72 | 50 | 3600 |  |  |  |  | 3600
1.4.4.3 | Additional Development based on feedback on Work Package 4 | Web Developer | 4 | 50 | 200 |  |  |  |  | 200
|  | Web Developer Consultant | 4 | 50 | 200 |  |  |  |  | 200
1.4.5 | End-User Documentation |  |  |  | 0 |  |  |  |  | 0
1.4.5.1 | Draft End-User Documentation based on Requirements | Control Manager | 24 | 45 | 1080 |  |  |  |  | 1080
1.4.5.2 | Review and Finalize End-User Documentation | Project Manager | 16 | 65 | 1040 |  |  |  |  | 1040
1.4.5.3 | Project Implementation Phase |  |  |  | 0 |  |  |  |  | 0
1.4.6 | Prerequisites |  |  |  | 0 |  |  |  |  | 0
1.4.6.1 | Installation of FIOS Business | Verizon | 1 | 0 | 0 | Verizon FiOS Business Plan (150Mbps). |  |  | 1319.88 | 1319.88 | Base Year Cost
1.4.6.2 | Installation and setup of Network Infrastructure (routers, firewall, cabling, etc.) | Implementation Lead | 24 | 55 | 1320 |  |  |  |  | 1320
1.5 | Installation and setup of All-In-One Printer, Laptops, Security Software | Implementation Lead | 16 | 55 | 880 |  |  |  |  | 880
1.5.1 | Conduct smoke tests of infrastructure (e.g. internet, hot spots, etc.) | Technical Lead | 16 | 55 | 880 |  |  |  |  | 880
1.5.1.1 | Installation |  |  |  | 0 |  |  |  |  | 0
1.5.1.2 | Install and configure SysPro ERP system | Technical Lead | 16 | 55 | 880 | SysPro ERP System |  |  |  | 880
1.5.1.3 | Install and configure Clover POS | Technical Lead | 16 | 55 | 880 | Clover POS System |  |  |  | 880
1.5.1.4 | Transfer legacy data into new SysPro ERP system | Implementation Lead | 16 | 55 | 880 |  |  |  |  | 880
|  | Technical Lead | 16 | 55 | 880 |  |  |  |  | 880
1.5.2 | Install and configure custom website | Implementation Lead | 16 | 55 | 880 |  |  |  |  | 880
|  | Technical Lead | 16 | 55 | 880 |  |  |  |  | 880
|  | Web Developer | 16 | 50 | 800 |  |  |  |  | 800
1.5.2.1 | Testing |  |  |  | 0 |  |  |  |  | 0
1.5.2.2 | Smoke test of overall systems | Technical Lead | 16 | 55 | 880 |  |  |  |  | 880
|  | Implementation Lead | 16 | 55 | 880 |  |  |  |  | 880
1.5.2.3 | Reinstall and follow-up testing of overall systems | Technical Lead | 12 | 55 | 660 |  |  |  |  | 660
|  | Implementation Lead | 12 | 55 | 660 |  |  |  |  | 660
1.5.2.4 | Schedule System Test and Validation | Technical Lead | 2 | 55 | 110 |  |  |  |  | 110
1.5.3 | Conduct System Test and Validation | Technical Lead | 24 | 55 | 1320 |  |  |  |  | 1320
|  | Implementation Lead | 24 | 55 | 1320 |  |  |  |  | 1320
1.5.3.1 | Schedule User Acceptance Testing | Technical Lead | 2 | 55 | 110 |  |  |  |  | 110
1.5.3.2 | Conduct User Acceptance Testing | Technical Lead | 20 | 55 | 1100 |  |  |  |  | 1100
1.5.3.3 | Analyze Defects and Correct | Web Developer | 16 | 50 | 800 |  |  |  |  | 800
1.5.3.4 | Conduct Final User Acceptance Testing | Technical Lead | 8 | 55 | 440 |  |  |  |  | 440
1.5.4 | Training |  |  |  | 0 |  |  |  |  | 0
1.5.4.1 | Provide User Training in use of SysPro ERP. | SysPro ERP | 12 | 0 | 0 |  |  |  |  | 0
1.5.4.2 | Provide User Training in use of Clover POS. | Clover POS | 8 | 0 | 0 |  |  |  |  | 0
1.5.4.3 | Provide User Training in use of custom website. | Control Manager | 8 | 45 | 360 |  |  |  |  | 360
1.5.4.4 | Deliver SysPro ERP, Clover POS, Website user manuals | Implementation Lead | 4 | 55 | 220 |  |  |  |  | 220
|  | Clover POS | 4 | 0 | 0 |  |  |  |  | 0
|  | SysPro ERP | 4 | 0 | 0 |  |  |  |  | 0
1.5.5 | Support and Maintenance |  |  |  | 0 |  |  |  |  | 0
1.5.5.1 | Hand-off of Project Deliverables | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.5.5.2 | Final Acceptance Status Meeting | Project Manager | 4 | 65 | 260 |  |  |  |  | 260
1.5.5.3 | Obtain Project Sponsor Acceptance | Project Sponsor | 0 | 0 | 0 |  |  |  |  | 0
1.5.6 | Go-Live | Project Manager | 0 | 65 | 0 |  |  |  |  | 0
| Grand Total | [8 empty] | 94985.88

## Rate (hidden)
Member | Role Assigned | Hourly Rate
Bruce Asberry | Project Manager | 65
Marco Antonio Rodriguez | Implementation Lead | 55
Mark Fowler | Control Manager | 45
Micheal Mays | Web Developer | 50
Tibletse Nigussie | Technical Lead | 55
Nous (Web Developer) | Web Developer Consultant | 50
Stephany Head | Project Sponsor | 0
Verizon | Verizon | 0
Clover POS | Clover POS | 0
SysPro ERP | SysPro ERP | 0