Name of the project: ZD Coffee and ZD shop

Team of the project: Group A

Owners: Marvel Sutih, Campion Lingany, Daniel Proto, Jamie Sunton, Crotus Ovelle, Martin Wawesh

Start Date: Wednesday August 1, 2018

Projected completion Date: Sunday November 15 evening

Project purpose or mission: ZD Coffee and ZD shop is purposing to avail quality coffee and an atmosphere of invitation to the students of NOVADA College and the surrounding. The project’s slogan which is very instrumental is “Eat a bagel, drink a joe and stay merry.”

Description and project product: completing the ZD Coffee and ZD shop project will be a business venture and the opening of a way to greater opportunities for the company. For instance, the shop will be an outcome of the first venture. The outcome of this project is an invitation atmosphere that will allow NOVADA College students to socialize as they study while enjoying ZD awesome Coffee. ZD’s plan is to accomplish these objectives in time and lead the team in order to avoid any unnecessary delays.

The 5 level deliverables include the following:

- Layout design of the building (shop)

- POS (IT) system and Wi-Fi installation

- Budget management to account for revenues and expenses

- Marketing organization after the shop is opened for product development in order to make the target population aware

- The training of staff or orientation on store operations as well as on safety

Objectives of the project

- To become the best coffee and shop operator in the locality

- Break even in the first month of business and operations

- Keep up to a gross margin of above 60 percent

ZD operation and the business Need:

Having more than 400 billion cups of coffee consumed on a daily basis, coffee turns out to be among the best beverages world over. It is sold in a wide range of business entities including bars and night clubs. This means that nearly everyone takes coffee in at least two days period. The opportunity is thus wide. Having the right venture and a good value proposition, a coffee shop can be a lucrative venture that is easy to operate.

Milestones:	a) Financial assessment on 1st August

b) Project approval on 3st August

c) Contact utilities and city for permits – 10th August

d) Evaluation of prospective suppliers and contractors – 10th August

e) Orders to be placed for material supply – 13th August

f) Construction to commence – 16th August

g) Order the balances of materials and equipment needed – 27th August

h) A complete installation of all materials that are needed -28th September

i) POS system setting up through completion -4th October

j) Installation of the final equipment – 5th October

k) Work finishing – final touches – 16th October

l) The grand opening – 18th October

Budget: 	a 3-months budget

|  | Estimated Labor | $10,800.00 |
| --- | --- | --- |
|  | Estimated Materials | $14,900.00 |
|  | Estimated Contractors | $15,000.00 |
|  | Estimated Equipment and Facilities | $23,000.00 |
|  | Estimated Permit Cost | $2,500.00 |
|  | Total Estimated Start-up Cost | $66,200 |
| Lease Espresso machine; $100. Phone (2 lines); $100. Garbage; $75. Insurance; $500. Internet / wifi / POS; $100. Electric / Water / sewer; $300. Lease payment for building; $2000. Tv; $100. payroll; $200. subtotal; $3475. Labor (4 ee’s + 1 mgr); $13680. Total monthly expenses; $17,155. Total 17,155 / 30 days in a month = 572 - this is the amount the coffee shop must sell each day to break even 572 / 15 hours per day = 38 per hour 38 / avg of 4.00 per sale = 9.5 sales per hour If we bought the espresso machine and building, it would increase start-up costs 165,000 and decrease monthly expenses by 2100.. Financial Data: Your Leasing Space (Physical Space); Notes:. Electrical Installations; $3,000. Counters; $1,800. Walls (4 - office and kitchen); $2,000. Lighting; $400. Shelving & storage; $800. Painting; $600. Flooring; $1,500. Plumbing; $1,500. Restroom Upgrading; $500. Vent Installations; $1,000. Sinks; $300. Alarm; $300. Display Cabinets; $800. Mop sink and Install; $400. Subtotal Building Materials; $14,900. Equipment / finish items. Two Grinders; $3,000. Refrigerator; $800. Freezer; $500. Mugs/Glasses; $400. Commercial Drip Coffee Maker; $600. Computer, Printer and POS system; $4,000. Chairs and Tables; $1,000. Outdoor furniture; $200. Smallwares; $500. Music System; $500. Electronic Scales; $300. Cleaning supplies; $200. Internal Displays and Signage; $200. Outside Signs and Displays; $800. TV; $800. Commercial dough mixer; $1,500. Oven; $3,000. Microwave; $300. Dishwasher; $700. Artwork and plants; $1,000. Subtotal Equipment; $20,300. Other Items. Coffee Beans Inventory; $1,000. Marketing; $500. Website Design; $500. Office Supplies; $200. Baking supplies; $500. Subtotal supplies; $2,700. Total equipment plus supplies; $23,000. GRAND TOTAL materials/equipment/supplies; $37,900. |

Risks and uncertainties

- Inadequate supplies – supply companies can run short of their products and this shakes our reliability to either.

- Permits are fond to delay – state protocol should be observed to the latter and compliance need to be adhered to which drags the process

- Inadequate suppliers- suppliers will consider things like distances to cover for transportation and other factors as a way of determining whether they supply or not

- Power blackouts

- In case equipment are faulty, the business runs into risks

- Faulty connection of power

- Licenses also delay which turns the business to hold

- Wasted food

- Building materials can be damaged

- Contractors can fail to deliver

- Sickness of the project implementers

- Closure of NOVADA College

- Obsolescence of some technologies used for construction

- Market failures

- Inflation of supply prices

| APPROVALS |  |  |
| --- | --- | --- |
| #### Type Name | #### Signature | #### Date |
| Project Manager Approval |  |  |
| Sponsor Approval |  |  |