	WBS
	Activity No.
	Description 
	Duration 
	Relationship 

	1
	MS1
	Start Project
	1
	No activity can start until MS1 has begun

	1.2.2
	1
	Install acoustic walls
	3
	Starts after MS1

	1.1.1
	2
	Build in lighting 
	4
	Cannot start until activity 1 is completed 

	1.2.2
	3
	Install remotely controlled curtain system  
	2
	Cannot start until activity 2 is completed 

	1.2.2
	4
	Place carpet 
	2
	Cannot start until activity 3 is completed 

	1.1.2
	5
	Install projection system  
	2
	Cannot start until activity 4 is completed. May be preformed concurrently with activity 6

	1.1.3
	6
	Install Smart Board 
	2
	Cannot start until activity 4 is completed. May be preformed concurrently with activity 5

	1.1.4
	7
	Build Wireless Wi-Fi connection 
	2
	Cannot start until activities 5 and 6 are completed 

	1.2.1
	8
	Assemble Conference Table  
	3
	Cannot start until activity 7 is completed. May be preformed concurrently with activities 9 and 10

	1.2.1
	9
	Assemble conference chairs 
	3
	Cannot start until activity 7 is completed. May be preformed concurrently with activates 8 and 10 

	1.2.1
	10
	Build a storage 
	2
	Cannot start until activity 7 is competed. May be preformed concurrently with activates 8 and 9

	1.1.1
	11
	Install High quality Sound system  
	3
	Cannot start until activities 8,9 and 10 are completed 

	1.1.2
	12
	Install microphones on conference table
	1
	Starts when activity 11 Starts

	1.1.3
	13
	Install Videoconferencing system  
	3
	Cannot start until activity 12 is completed 

	1.2.2
	14
	Put Aesthetic decoration 
	2
	Cannot start until activity 13 is completed 

	1.1
	15
	Test equipment 
	2
	Cannot start until activities 13 and 14 are completed 

	1
	MS2
	Finish project 
	1
	Cannot start until activity 15 is completed 
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