| WBS | Activity No. | Description | Duration | Relationship |
| --- | --- | --- | --- | --- |
| 1 | MS1 | Start Project | 1 | No activity can start until MS1 has begun |
| 1.2.2 | 1 | Install acoustic walls | 3 | Starts after MS1 |
| 1.1.1 | 2 | Build in lighting | 4 | Cannot start until activity 1 is completed |
| 1.2.2 | 3 | Install remotely controlled curtain system | 2 | Cannot start until activity 2 is completed |
| 1.2.2 | 4 | Place carpet | 2 | Cannot start until activity 3 is completed |
| 1.1.2 | 5 | Install projection system | 2 | Cannot start until activity 4 is completed. May be preformed concurrently with activity 6 |
| 1.1.3 | 6 | Install Smart Board | 2 | Cannot start until activity 4 is completed. May be preformed concurrently with activity 5 |
| 1.1.4 | 7 | Build Wireless Wi-Fi connection | 2 | Cannot start until activities 5 and 6 are completed |
| 1.2.1 | 8 | Assemble Conference Table | 3 | Cannot start until activity 7 is completed. May be preformed concurrently with activities 9 and 10 |
| 1.2.1 | 9 | Assemble conference chairs | 3 | Cannot start until activity 7 is completed. May be preformed concurrently with activates 8 and 10 |
| 1.2.1 | 10 | Build a storage | 2 | Cannot start until activity 7 is competed. May be preformed concurrently with activates 8 and 9 |
| 1.1.1 | 11 | Install High quality Sound system | 3 | Cannot start until activities 8,9 and 10 are completed |
| 1.1.2 | 12 | Install microphones on conference table | 1 | Starts when activity 11 Starts |
| 1.1.3 | 13 | Install Videoconferencing system | 3 | Cannot start until activity 12 is completed |
| 1.2.2 | 14 | Put Aesthetic decoration | 2 | Cannot start until activity 13 is completed |
| 1.1 | 15 | Test equipment | 2 | Cannot start until activities 13 and 14 are completed |
| 1 | MS2 | Finish project | 1 | Cannot start until activity 15 is completed |