## Sheet1
Cost Estimate
Project Name: | Date:
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 200 | 65 | 13000 |  |  | 0 | 13000 |  | 13000
2. Planning | 600 | 60 | 36000 |  |  | 0 | 36000 |  | 36000
3. Executing |  |  | 0 |  |  | 0 | 0 |  | 0
3.1 Course design and development |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.1 Supplier management training | 600 | 60 | 36000 | 600 | 150 | 90000 | 126000 | 100000 | 226000
3.1.2 Negotiating skills training | 300 | 55 | 16500 | 300 | 150 | 45000 | 61500 | 50000 | 111500
3.1.3 Project management training | 400 | 60 | 24000 | 400 | 150 | 60000 | 84000 | 50000 | 134000
3.1.4 Software applications training | 400 | 60 | 24000 | 400 | 150 | 60000 | 84000 | 50000 | 134000
3.2 Course administration | 400 | 55 | 22000 | 300 | 250 | 75000 | 97000 | 80000 | 177000
3.3.Course evaluation | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500
3.4 Stakeholder communications | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500
4. Monitoring and Controlling | 500 | 55 | 27500 |  |  | 0 | 27500 |  | 27500
5. Closing | 200 | 55 | 11000 |  |  | 0 | 11000 |  | 11000
Subtotal | [8 empty] | 903000
Reserves |  |  | 0 |  |  | 0 | 0 |  | 90300
Total | 4200 |  | 243000 | 2000 | 850 | 330000 | 573000 | 330000 | 993300
Assumptions