Technology

Name:

Professor:

Course Title:

Institution:

Date:

The following is the Work Breakdown Structure for an Email Upgrade Project:

- Evaluate User & System Requirements

  - Assess User Needs and Requirements

    - Note User Complaints and Problems

    - Record  User Requests

    - Librate User Requests and Complaints

    - Prioritize User Requirements

  - Appraise System Requirements

    - Examine  System Hardware Requirements

    - Canvass System  Interface Requirements

    - Analyze Software Interface Requirements

- Evaluate ODHS Network Suitability

  - Appraise Network Infrastructure

    - Examine Network Capabilities

    - Record Network Weaknesses

  - Identify Necessary Hardware Upgrades

    - Examine Potential Hardware Upgrades

    - Choose Necessary Hardware Upgrades

- Conduct E-mail System Selection

  - Identify Potential  Vendors

    - Assess Vendor Capabilities

    - Assess Vendor Costs

    - Hit Each Vendor

- Upgrade ODHS Network & Hardware

  - Upgrade Hardware

    - Create Hardware Upgrade Schedule

    - Install New Hardware

    - Examine New Hardware

  - Upgrade Network

    - Develop Network Upgrade Schedule

    - Install New Network

    - Test New Network

- Develop Email Training

  - Create Training  for E-mail System

    - Develop Employee Training

    - Develop User Community Training

  - Conduct Email-System Training

    - Train Employees

    - Conduct Various User Community Training Sessions

- Deploy E-mail  System

  - Structure Deployment Plan

    - Prioritize Deployment activities

    - Assess Schedule Risks

    - Create Deployment Schedule

  - Execute Deployment Plan

    - Inform All Users of Deployment Date

    - Go Live with New System

| TASK NAME | START DATE | END DATE |
| --- | --- | --- |
| 1.0 Evaluate User & System Requirements | 12/1/2019 | 12/21/2019 |
| 1.1 Assess User Needs and Requirements | 12/1/2019 | 12/16/2019 |
| 1.1.1 Note User Complaints and Problems | 12/1/2019 | 12/9/2019 |
| 1.1.2 Record User Requests | 12/1/2019 | 12/9/2019 |
| 1.1.3 Librate User Requests and Complaints | 12/9/2019 | 12/14/2019 |
| 1.1.4 Prioritize User Requirements | 12/14/2019 | 12/17/2019 |
| 1.2 Appraise System Requirements | 12/17/2019 | 12/20/2019 |
| 1.2.1 Examine System Hardware Requirements | 12/17/2019 | 12/19/2019 |
| 1.2.2 Canvass System Interface Requirements | 12/17/2019 | 12/21/2019 |
| 1.2.3 Analyze Software Interface Requirements | 12/17/2019 | 12/21/2019 |
| 2.0 Evaluate ODHS Network Suitability | 12/21/2019 | 1/10/2020 |
| 2.1 Appraise Network Infrastructure | 12/21/2019 | 12/30/2019 |
| 2.1.1 Examine Network Capabilities | 12/21/2019 | 12/30/2019 |
| 2.1.2 Record Network Weaknesses | 12/21/2019 | 12/30/2019 |
| 2.2 Identify Necessary Hardware Upgrades | 12/30/2019 | 1/10/2020 |
| 2.2.1 Examine Potential Hardware Upgrades | 12/30/2019 | 1/8/2020 |
| 2.2.2 Choose Necessary Hardware Upgrades | 1/8/2020 | 1/10/2020 |
| 3.0 Conduct E-mail System Selection | 1/10/2020 | 2/19/2020 |
| 3.1 Identify Potential Vendors | 1/10/2020 | 2/9/2020 |
| 3.1.1 Assess Vendor Capabilities | 1/10/2020 | 1/15/2020 |
| 3.1.2 Assess Vendor Costs | 1/15/2020 | 1/25/2020 |
| 3.1.3 Hit Each Vendor | 1/25/2020 | 1/30/2020 |
| 4.0 Upgrade ODHS Network & Hardware | 2/19/2020 | 4/20/2020 |
| 4.1 Upgrade Hardware | 2/19/2020 | 3/30/2020 |
| 4.1.1 Create Hardware Upgrade Schedule | 2/19/2020 | 3/5/2020 |
| 4.1.2 Install New Hardware | 3/5/2020 | 3/25/2020 |
| 4.1.3 Examine New Hardware | 3/25/2020 | 4/9/2020 |
| 4.2 Upgrade Network | 4/9/2020 | 4/14/2020 |
| 4.2.1 Develop Network Upgrade Schedule | 4/9/2020 | 4/17/2020 |
| 4.2.2 Install New Network | 4/17/2020 | 4/18/2020 |
| 4.2.3 Test New Network | 4/18/2020 | 4/20/2020 |
| 5.0 Develop Email Training | 2/19/2020 | 4/20/2020 |
| 5.1 Create Training for E-mail System | 2/19/2020 | 3/30/2020 |
| 5.1.1 Develop Employee Training | 2/19/2020 | 3/10/2020 |
| 5.1.2 Develop User Community Training | 3/10/2020 | 3/30/2020 |
| 5.2 Conduct Email-System Training | 3/30/2020 | 4/20/2020 |
| 5.2.1 Train Employees | 3/30/2020 | 4/6/2020 |
| 5.2.2 Conduct Various User Community Training Sessions | 4/6/2020 | 4/20/2020 |
| 6.0 Deploy E-mail System | 4/20/2020 | 5/10/2020 |
| 6.1 Structure Deployment Plan | 4/20/2020 | 4/30/2020 |
| 6.1.1 Prioritize Deployment activities | 4/20/2020 | 4/23/2020 |
| 6.1.2 Assess Schedule Risks | 4/23/2020 | 4/28/2020 |
| 6.1.3 Create Deployment Schedule | 4/28/2020 | 4/30/2020 |
| 6.2 Execute Deployment Plan | 4/30/2020 | 5/10/2020 |
| 6.2.1 Inform All Users of Deployment Date | 4/30/2020 | 5/8/2020 |
| 6.2.2 Go Live with New System | 5/8/2020 | 5/10/2020 |

Reference

Hieb, B., Denison, D. R., Ramachandran, R., & Fellows, H. (2014). U.S. Patent No. 8,898,660. Washington, DC: U.S. Patent and Trademark Office.

Wang, Y. Y., Wang, Y. S., & Lin, T. C. (2018). Developing and validating a technology upgrade model. International Journal of Information Management, 38(1), 7-26.