Project Control

Status Meeting Agenda

Meeting: December 05, 2018 at Central Park at 3:00 p.m.

Project: Installing a pool

Meeting #1

| Agenda Item | Facilitator | Length of Discussion |
| --- | --- | --- |
| Advertisement of project | Project Manager | 25 minutes |
| Selection of advertising firm | Project Manager | 13 minutes |
| Duration of advertisement | Project Manager | 10 minutes |
| Costs incurred | Project Manager | 15 minutes |

| Action Items | Who is Responsible? | Finish Date |
| --- | --- | --- |
| Create theme of advertisement | Joey O’Connor | December 5, 2018 |
| Create advertisement plan | Peter Drury | December 7, 2018 |
| Meeting with advertising firm | Tim Cahill | December 13, 2018 |
| Updating progress | Mackenzie Edwards | December 20, 2018 |

Meeting #2

December 28, 2018 at project site 9:00 a.m.

| Agenda Item | Facilitator | Length of Discussion |
| --- | --- | --- |
| Progress of advertisement | Project Manager | 10 minutes |
| Does the advertisement capture the purpose of project? | Project Manager | 15 minutes |
| Project beneficiaries’ opinion | Project Manager | 15 minutes |
| How much is left for completion? | Project Manager | 5 minutes |

| Action Items | Who is Responsible? | Finish Date |
| --- | --- | --- |
| Progress Report of advertisement | Mabon Lee | February 2, 2018 |
| Make more advertisements | William Georges | February 2, 2018 |
| Stakeholder Evaluation | Joe Turner | February 2, 2018 |
| Updated Project Advertisement Timeline | Jessica Biel | February 2, 2018 |

Issue Tracking Worksheet

| Issue | Rating of Importance | Person Responsible | Notes | Resolution Date |
| --- | --- | --- | --- | --- |
| Not enough funds | 8 | Mabon Lee | Project is reviewed | January 10, 2018 |
| Advertisement of project is not adequate | 7 | Tim Cahil | Budget did not meet quality expected | January 15, 2018 |
| Not enough people on team | 7 | Mackenzie Edwards | Insufficient expertize in relation to advertisement | January 19, 2018 |

Status Report Form

| Name | Scope | CPI | SPI | Project Manager | Issue | Risk | Recent Accomplishments | Upcoming Accomplishments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Design | Will create design | 1.5 | 1.5 | Tim Cahil | N/A | Wrong impression of project | Created design | Location could be found |
| Location | Will identify suitable location | 1.4 | 1.4 | Mackenzie Edwards | N/A | Location not as per expectations | Location work | Meeting advertising firm |
| Advertising firm | Will meet advertising firm | 1.4 | 1.4 | Mabon Lee | N/A | May not reach an agreement | Identifying best advertising firm | Build team |
| Team | Will assemble team | 1.4 | 1.4 | William Georges | N/A | May not have enough people | Built team | Gantt Chart |
| Gantt Chart | Will create project timeline | 1.4 | 1.4 | Joe Turner | N/A | Might be off | Gantt chart completed | Project Completion |