## Slide 1: Project kickoff. Library management system.
Student name.
Name of the institution.
Name of the course.

## Slide 2: Goals and objectives.
To provide easy access of books.
To enable a 24 hours access of books.
Increase the number of people with access to the library
Reduce manual work and the risk loosing books.
Notes: Students will be able to access different type of books by logging into their accounts in the system.
Students will be able to access books at different points, whether they are at school or at their homes.
The system will enable more than one student to access the same book at the same time.
The system will reduce manual work and the risk of loosing book because the books will be accessed online.

## Slide 3: Project scope.
In scope.
Support windows and android.
Features.
Student portal.
Student registration.
Student login
Search button.
Borrow book.
Message button.
Notes: The system will support window and android devices. It will be accessible through web browsers.
Features.
Student portal. This is the user interface that the student will be able to see after opening the library management system.
Student registration. There will be option for new student to register to the system.
Student login. After registration the student will be directed to the login section in order to access library services.
Search button. It will enable students to search different type of books within the system
Borrow book. After finding the book, the student will be directed to the borrow a book option which will give them the option to access the book online.
Message button. This feature will enable students to communicate with the librarians so that they can be assisted incase they face any challenge when using the system

## Slide 4: Project scope (continuation)
Administration portal.
a. Check in students.
b. Update new books.
c. Chat with students.
Out of scope.
Support IOS.
Create an IOS application (future)
Notes: The administration portal will be managed by the librarians.
Check in students. The librarians will be able to check in students with their specific registration numbers to prevent outsiders from accessing the system.
Update new books. This option will allow the librarians to update new books to the system.
Chat with students. This option will allow librarians to view student messages and reply to their queries.
Out of scope
Support IOS. In future the system will be upgraded to support IOS products.

## Slide 5: Budget.
Approximated project cost. $5900
Notes: The budget will include.
Four laptops, each with a cost of $500 which totals to $2000
Software's
Microsoft office $300*4=$1200
windows 8, $300 * 4=$1200
Labor. $500
miscellaneous cost $1000

## Slide 6: Implementation time.
1. Design- week 1 & 2.
System features.
Conditions by which the system will be acceptable.
2. Coding. Week 4,5,6,7.
Student portal.
Admin portal
Notes: Week 1 and 2.
Deign a system prototype.
Receive specifications by which the product will be acceptable by the owner.
Week 4,5,6 $ 7.
Write the actual code of the system for both the student portal and admin(librarian) portal.

## Slide 7: Implementation time (continuation)
3. Testing and debugging. Weeks. 8,9,10
Documentation.
User acceptance.
4. Week 11
Release.
Notes: Week 8,9 & 10.
Test the existence of any bugs in the codes and correct them.
Document the code to allow easy upgrading.
Present the system to the owner.
Week 11.
Hand the system to the owner.

## Slide 8: Risk factors.
1. Availability of resources.
Project manager having to handle multiple projects.
Availability of computers.
Availability of experts to teach students and librarians how to use the system.
Notes: Availability of resources.
The project manager might be committed in attending other projects.
The students may not be able to afford computers and access the system.
There might be no enough skilled manpower to explain to the whole students how the system works.

## Slide 9: Risk factors (continuation)
Technology factor.
Creation of a live chat feature.
Compatibility issues with different devices.
Hackers.
Notes: Technology factor.
The live chat feature may not be helpful when the specific book the student is requesting for is not available.
The system may not be compatible with IOS devices.
The system might be prone to hackers who may coordinate with students to gain access to the system.

## Slide 10: Project team roles and responsibilities.
.
[Full name]
Project manager
[Full name]
Product owner.
[Full name]
Developer PHP & css
[Full name]
Developer database mysql
[Full name]
Developer reporting
[Full name]
Tester. Quality assurance and user requirements
Notes: Project manager supervises the project from its initiation up to the time when it is handed over to the owner.
Product owner gives specification of the required software.
Php and css developer writes the php and css codes.
The database developer creates the system database to host all the library system details.
The developer reporting reports the progress of the project to the project manager.
The tester ensures that the project meets all the requirements before it is handed over to the owner.

## Slide 11: Communication between the project team and stakeholders.
Project team members meeting.
Updating each other on the project progress through phone calls and emails .
Exchange and sharing of project folders within the project team.
Notes: The project team members should meet regularly to determine the progress of the project.
The team should update the progress through phones and emails and help one another in solving different challenges.
The team should exchange folders to ensure each member working on their parts in order to prevent setbacks during implementation.

## Slide 12: References.
O’ Reagan. (2017). Software project management: Concise guide to software engineering.
Springer. 27-46.
doi: 10.1007/978-3-319-57750-0_2
Scheid, J. (n. d). How to implement the WBS methodology. Bright Hub PM. Retrieved from
https://www.brighthubpm.com/project-planning/75514-implementing-wbs-methodology/