## 3.15
3.15
| Activity | Time (weeks) |  | Activity | Immediate
Predecessor
| A | 6 |  | A | n/a
| B | 7 |  | B | n/a
| C | 3 |  | C | A
| D | 2 |  | D | A
| E | 4 |  | E | B
| F | 6 |  | F | B
| G | 10 |  | G | C, E
| H | 7 |  | H | D, F
| Activity | Time (weeks) | Early | Early | Late | Late | Slack | Critical
|  |  | Start (ES) | Finish (EF) | Start (LS) | Finish (LF)
| A | 6 | 0 | 6 | 2 | 8 | 2 | No
| B | 7 | 0 | 7 | 0 | 7 | 0 | Yes
| C | 3 | 6 | 9 | 8 | 11 | 2 | No
| D | 2 | 6 | 8 | 12 | 14 | 6 | No
| E | 4 | 7 | 11 | 7 | 11 | 0 | Yes
| F | 6 | 7 | 13 | 8 | 14 | 1 | No
| G | 10 | 11 | 21 | 11 | 21 | 0 | Yes
| H | 7 | 13 | 20 | 14 | 21 | 1 | No
|  |  |  | 21 | weeks, total project completion
Critical activity path is B, E, G

## 3.17
Bill Fennema, president of Fennema Hospitality, has developed the tasks, durations, and predecessor relationships in the following table for building new motels. Draw the AON network and answer the questions that follow.
| Activity | Immediate | Time estimates (weeks) |  |  | Expected | Variance
|  | Predecessor | Optimistic | Most Likely | Pessimistic | Time
| A | n/a | 4 | 8 | 10 | 7.6667 | 1
| B | A | 2 | 8 | 24 | 9.6667 | 13.4444
| C | A | 8 | 12 | 16 | 12 | 1.7778
| D | A | 4 | 6 | 10 | 6.3333 | 1
| E | B | 1 | 2 | 3 | 2 | 0.11111
| F | E, C | 6 | 8 | 20 | 9.6667 | 5.4444
| G | E, C | 2 | 3 | 4 | 3 | 0.11111
| H | F | 2 | 2 | 2 | 2 | 0
| I | F | 6 | 6 | 6 | 6 | 0
| J | D, G, H | 4 | 6 | 12 | 6.6667 | 1.7778
| K | I, J | 2 | 2 | 3 | 2.1667 | 0.027778
Estimated Path Time
| Paths |  | Variance
| A-D-J-K | 22.8333
| A-C-G-J-K | 31.5
| A-C-F-I-K | 37.5
| A-B-E-G-J-K | 31.1667
| A-B-E-F-I-K | 37.1667
| A-C-F-H-J-K | 40.1667 | 10.0278
| A-B-E-F-H-J-K | 39.8333
c) Based on the calculation of estimated times, what is the critical path?
A-C-F-H-J-K is the critical path
d) What is the estimated time of the critical path?
40.17 weeks is the estimated time of the critical path.
e) What is the activity variance along the critical path?
Activity variance along the critical path is 10.03
f) What is the probability of completion of the project before week 36?
| 3.1667 | Standard deviation
| -1.3158 | 36 weeks - estimated time on critical path / standard deviation
| 0.094122 | Normal statistical distribution formula
| 9.412% | chance that the project will be completed before week 36
K