## Slide 1: Project Management and Event Implementation
Dr. Poudevigne

## Slide 2: Objectives
Describe the necessity of project management in the management of sport & fitness events
Use project management tools to plan and conduct a successful event
Outline the phases of project management

## Slide 3: Assignment
Read Chapter 6 and 7
Read through these slides
Based on your reading from Chapters 6 and 7, write a 1-page outline addressing:
  the types of events that can be hosted at your facility (provide a short description of each);
  General planning phase for events; and
  Scheduling and timing of events.
  Due in Dropbox by Deadline in syllabus

## Slide 4: Project Management
The dynamic process of organizing and managing appropriate resources in a controlled and structured manner to deliver the clearly defined work required to complete a project within defined scope, time, and often, cost constraints (Patel, 2008; Young, 2007).
The integration of all the management tasks necessary to oversee the work before, during, and after the event has occurred.
Project: a temporary and one-time venture undertaken to create a unique product with specific outcomes and benefits.

## Slide 5: Project Management Triangle
A challenge of project management is to ensure the event can be delivered within the defined constraints; those constraints being time, scope, and cost.
  Time: the amount of time to complete the project
  Cost: the amount of money budgeted to complete the project
  Scope: the work to be done to implement the project
If the project falls behind schedule, costs go up and/or the work on the project changes if quality is to be maintained.

## Slide 6: Resource Allocation
Another challenge of project management is to ensure the proper allocation and assimilation of the inputs (e.g., people, money, time, etc.) to meet the objectives of the event.
Project management tools:
  Help the event manager systematically define the tasks necessary to meet overall objectives
  Delegate those tasks to the right people
  Allocate financial resources appropriately
  Coordinate when the tasks must be completed

## Slide 7: Phases of Project Management
A main aim of project management is to control risk and potential failure by providing a clear direction that aligns with the strategic goals and objectives for the event.
Five core phases:
  Initiation
  Planning
  Implementation
  Monitoring
  Shutdown

## Slide 8: EMBOK
International Event Management Body of Knowledge (EMBOK) has conceptualized a three dimensional depiction of the phases, domains, and processes necessary to create and deliver sport & fitness events.

## Slide 9: Initiation
The initiation phase allows sport & fitness event organizers to define the event, set objectives, and determine the sport & fitness event’s feasibility.
A feasibility study will detail the viability of a sport & fitness event and the managerial requirements necessary to deliver it.
The end of the initiation phase is often marked by a red or green light decision to continue to the planning stages.

## Slide 10: Planning
Planning is straightforward and can be considered a process of asking questions (Young, 2007), such as:
    What actions need to be taken?
    When will these actions occur?
    Who is going to take on these actions?
    What resources (both human, financial, and supplies/equipment) are required for these actions?
The planning stage is very dynamic and continuous and sport & fitness event managers must remain proactive and diligent.
It is wise not to plan all the detail at the outset to avoid reworking the plan and wasting valuable time.

## Slide 11: Implementation
Each domain area will have a specific plan that contributes to the overall event plan that must detail how and when the work will be completed.
Once the work plan is complete, managers have the ability to confirm that all tasks (Young, 2007):
  Are allocated for someone to action
  Have financial resources allocated to them (if necessary), which allows for monitoring control over budget and spend
  Are realistic and achievable given the assigned time constraints

## Slide 12: Monitoring/Control
Monitoring and control systems are implemented to ensure that performance standards are achieved as the sport & fitness event is executed.
According to Young (2007, 2013), there are three operating modes:
    Measuring: to determine progress through formal and informal reporting
    Evaluating: to determine the cause of deviations from the plan and how to react
    Correcting: taking actions to correct the deviations from the plan
Preventative controls are established in the planning stages and continue into execution.

## Slide 13: Closure/Shutdown
Shutdown requires proper planning and execution to ensure nothing is lost, equipment is returned properly, and the flow of those involved occurs seamlessly.
Shutdown is the most forgotten element of the project.
Like the planning and execution stages, the shutdown should include a work breakdown structure, task and responsibility checklists, and a schedule, which is subject to risk analysis.

## Slide 14: Tools of Project Management
Software:
  Copper Project, Viewpath, eTask-it
Software systems:
  Microsoft Project, OpenProj
Run sheets
Checklists
Floor plans
Flow diagram
WBS: tasks broken down into manageable parts
Gantt chart: a bar chart that illustrates the various tasks in a time-sequence order
PERT chart: illustrates the tasks, duration, and dependency information