## Activity List
Porta-Vac Project
Activity List for the PORTA-VAC Project
| Activity | Description | Immediate Predecessor | Estimated Completion Time (weeks)
| A | Develop product design | --- | 6 | Instructions:
1. Draw the PERT Diagram on a separate sheet of paper based on this Activity List.
| B | Plan market research | --- | 2
| C | Prepare routing | A | 3 | 2. Check the next sheet for a solution and compare your work!
| D | Build prototype | A | 5
| E | Prepare marketing brochure | A | 3 | 3. Continue to the next sheet for further instructions.
| F | Prepare cost estimate | C | 2
| G | Do preliminary design testing | D | 3
| H | Complete Market survey | B, E | 4
| I | Prepare pricing and forecast report | H | 2
| J | Prepare final report | F, G, I | 2

## Project Flow
Porta-Vac Project
| Format |  |  |  |  | Example
| Earliest Start | Activity Name | Earliest Finish | Slack |  | 1 | Z | 3 | 3
| Latest Start | Activity Duration | Latest Finish |  |  | 4 | 3 | 6
[7 empty] | 9 | C | 11 | 3 | 20 | F | 21 | 3 |  | 31 | J | 32 | 3
[7 empty] | 10 | 2 | 11 |  | 21 | 3 | 23 |  |  | 32 | 3 | 34
|  | 1 | A | 5 | 4 |  | 12 | D | 16 | 4 | 22 | G | 24 | 3
|  | 2 | 6 | 6 |  |  | 13 | 4 | 16 |  | 24 | 3 | 26 | [6 empty] | Finish
Start
[7 empty] | 17 | E | 19 | 2
[7 empty] | 18 | 2 | 20
|  | 7 | B | 8 | 2 | [5 empty] | 25 | H | 28 | 4 |  | 29 | I | 30 | 2
|  | 6 | 3 | 8 | [6 empty] | 26 | 5 | 30 |  |  | 30 | 2 | 31
| Instructions: (see class notes for more details) | [12 empty] | Questions:
Note: Activity Times are listed on the Activity List.
[14 empty] | 1. What is the expected completion time? |  |  |  |  | 32 WEEKS
Step 1: Perform a forward pass -- computing the Earilest Start and Earliest Finish times. Insert these in the TOP row.
| Step 2: Perform a backward pass -- computing the Latest Finish and Latest Start times. Insert these in the BOTTOM row. | [12 empty] | 2. Where is the Critical Path? |  |  |  |  | A, D & G
| Step 3: Calculated the slack time for each activity. Insert this in the YELLOW box. | [13 empty] | (describe by the series of letter for the activities on the Crtical Path)
Step 4: Determine the Critical Path.
Then, proceed to the next sheet to determine the RISK of the project.

## Project Risk
Porta-Vac Project
| Instructions: | [8 empty] | Questions:
| Complete the tables below to answer the questions to the right. | [8 empty] | 1. What is the probability that this project will be completed within the goal of 20 weeks? | [6 empty] | 1%
[10 empty] | 2. What is the probability that this project will be completed faster, within 19 weeks? | [6 empty] | 1%
|  | Data given by Porta-Vac Production Leaders |  |  | (see formulas and hints in green to the right) |  |  |  |  | A-E-H-I-J | A-C-F-J | A-D-G-J | B-H-I-J
| Activity | Optimistic (a) | Most Probable (m) | Pessimistic (b) | Expected Completion Time (weeks) | Variance (weeks^2) | Slack (weeks) | On critical Path? (Yes=1 or No=blank) |  | Path 1 (Yes=1 or No=blank) | Path 2 (Yes=1 or No=blank) | Path 3 (Yes=1 or No=blank) | Path 4 (Yes=1 or No=blank)
| A | 4 | 5 | 12 | 3.5 | 1.7778 | 1.7222 | 1 |  | 1 | 1 | 1 | 1
| B | 1 | 1.5 | 5 | 1.25 | 0.44444 | 0.80556 | 1 |  | 1 | 1 | 1 | 1
| C | 2 | 3 | 4 | 1.5 | 0.11111 | 1.3889 | 1 |  | 1 | 1 | 1 | 1
| D | 3 | 4 | 11 | 3 | 1.7778 | 1.2222 |  |  | 1 |  | 1
| E | 2 | 3 | 4 | 1.5 | 0.11111 | 1.3889 | 1 |  | 1 | 1 | 1 | 1
| F | 1.5 | 2 | 2.5 | 1 | 0.027778 | 0.97222 | 1 |  | 1 | 1 | 1 | 1
| G | 1.5 | 3 | 4.5 | 1.5 | 0.25 | 1.25 | 1 |  | 1 | 1 | 1 | 1
| H | 2.5 | 3.5 | 7.5 | 2.25 | 0.69444 | 1.5556 | 1 |  | 1 | 1 | 1 | 1
| I | 1.5 | 2 | 2.5 | 1 | 0.027778 | 0.97222 | 1 |  | 1 | 1 | 1 | 1
| J | 1 | 2 | 3 | 1 | 0.11111 | 0.88889 |  |  |  |  | 1
[5 empty] | 17.5 | 5.3333 | 12.1667 | 8
[9 empty] | Expected completion time= | 17.5 |  |  |  | weeks |  | (Hint: Try =SUMPRODUCT(Path,Expected Completion Time)
|  | Goal to complete = | 20 | weeks |  |  |  |  | Path variance= | 5.33 |  |  |  | weeks-squared |  | (Hint: Same =SUMPRODUCT as above)
[9 empty] | Path StDev= | 17.5 |  |  |  | weeks |  | (Hint: take the square-root of the variance. =SQRT(x)
[9 empty] | z-score= | 2.5
[9 empty] | Probability to complete within Goal = | 1% |  |  |  |  | Note: P = NORM.S.DIST(z-score), as Standard-Normal Distribution has a Mean=0 and StDev=1.
[9 empty] | Probability to complete Critical Path on-time = | 1%
[9 empty] | Probability to complete all paths by the goal = | 1% |  | Note: All tasks must be completed on time, not just the Critical Path. Therefore, P(all) = P1 * P2 * P3 * P4
Hint: Change the goal in cell D21, then paste the answers above.