## Sheet1
EarthMover Project
"Current project has a critical path of 30 days. You must complete the job by at least day 26!"
|  | NORMAL |  |  | CRASH
| Activity | Time (weeks) | Cost |  | Best Time (weeks) | Activity Crash Cost ($) | Time reduction (weeks) | Crash Cost ($/week)
| A | 4 | 80000 |  | 5 | 20000 | -1 | -20000
| B | 2 | 100000 |  | 4 | 0 | -2
| C | 2 | 50000 |  | 2 | 50000 | 0 | 0
| D | 3 | 150000 |  | 3 | 150000 | 0 | 0
| E | 1 | 180000 |  | 2 | 70000 | -1 | -70000
| F | 5 | 300000 |  | 7 | 180000 | -2 | -90000
| G | 1 | 100000 |  | 2 | 0 | -1
| H | 3 | 450000 |  | 5 | 350000 | -2 | -175000
| I | 5 | 350000 |  | 4 | 300000 | 1 | 300000
|  | Goal to complete by: | 26 | weeks | <---- Change this goal from the currect 30 weeks to the new 26 week target!
Objective Function |  |  |  |  | Then run SOLVER to find the least expensive way to reach your goal !!!
| Min cost to CRASH |  | 25000
Xi = earliest finish time for activity i |  |  | EF-limit |  | Yi = the amount of time activity i is crashed |  |  | Max crash available |  | New time
A | 6 | = | 4 |  | A | 0 | <= | -1 | A | 4
B | 10 | = | 6 |  | B | 0 | <= | -2 | B | 2
C | 9 | = | 6 |  | C | 0 | <= | 0 | C | 2
D | 16 | = | 9 |  | D | 0 | <= | 0 | D | 3
E | 13 | = | 7 |  | E | 0 | <= | -1 | E | 1
F | 20 | = | 11 |  | F | 0 | <= | -2 | F | 5
G | 22 | = | 12 |  | G | 0 | <= | -1 | G | 1
H | 28 | = | 15 |  | H | 0 | <= | -2 | H | 3
I | 30 | = | 17 |  | I | 0 | <= | 1 | I | 5
|  | Note: | EF = EF of previous + t |  |  |  | Non-negativity constraints
New t = Original t - Crash
| New Finish time |  | Goal
H | 28 | <= | 26
I | 30 | <= | 26