Time to Work on the Doctoral Capstone

Planned dates- 1st august to 15th august

Writing days- Mondays, Tuesdays, Thursdays, Sundays

Non-writing days- Wednesdays. Fridays and Saturdays

Writing days

- Working time- 6 AM to 9 AM

- Resting time- 9am- 11am

- Family time- 1pm- 3pm

- Friend’s time- 4–6 PM

- Sundays- study about topics to write throughout the week

Non- writing days

Random chores and activities

Week 1

- Saturday – free day

- Sunday- setting of the capstone topic and doing background research

- Mondays – reviewing the applicable writing formats

- Tuesday- asking topic verification from the professor

- Wednesday- free day; topic approval by the professor

- Thursday- researching the ground to collect responses

- Friday- free day

- Saturday- free day

- Sunday- a compilation of responses and result tabulation

Week 2

- Monday- writing title and problem statement

- Tuesday- writing purpose and significance of the paper

- Wednesday- writing the background, framework and the hypothesis

- Thursday- writing nature of the study and sources of data

- Friday- free day

- Saturday- free day

- Sunday- writing limitations and challenges of the study. Writing the references

- Monday- proofreading the whole paper and paper submission

This schedule will help me avoid procrastination and build my dedication to the process of writing the paper. I picked to work in the morning hours when there are fewer disruptions and noise in the environment. Waking up early will prompt me to have an early sleep and prepare me for the morning task. The two-week timeframe is sufficient for writing and submitting the paper. It is long enough to give me time to research and peruse my work before submission and short enough to ensure that my attention does not drift from the paper. Sunday afternoons are usually quiet, and I chose it as the time to do my weekly research. If no major disruptions occur, I plan to follow the timetable to the letter.